## Cover_notes
Notes
A full set of times for lower port operations is included in the sheet 'Full set of times'. This has been extracted from Iain Farquhar's maintenance durations spreadsheet, IDM refernce EFDA_D_2NBXBQ version 2. The equations have all been converted to numbers to avoid missing links. Selected times from this large worksheet have been extracted and added to the 'Selected_times' worksheet.

## Selected_times
Approach time |  |  | Time (hours)
Survey hot cell and all in-cell equipment | Deploy in-cell inspection and handling system, and required tooling, into the hot cell | Logistics | 0.22
Remove Bioshield Plug | Collect Bioshield door movers from hot cell interface | Logistics | 0.22
Open the Vacuum Closure Plate door | Collect VCP handling frame door movers from hot cell interface | Logistics | 0.2126
Open the Vacuum Closure Plate door | Move test mass to lower port | Movement | 0.18056
Performance time
Survey hot cell and all in-cell equipment | Collect MPR from the hot cell interface | Logistics | 0.336
Survey hot cell and all in-cell equipment | Place Multi-purpose robot (MPR) into RM laydown area | Logistics | 0.336
Install threshold rails and in-port deployment system | Position rails using overhead crane | Logistics | 0.38
Remove vacuum pump service connection | Install Mechanical pipe connection tooling to the first pipe module joint | Operation | 0.3056
Return time
Remove vacuum pump service connection | Move to lower port | Movement | 0.18056
Remove vacuum pump service connection | Move the removed pipe module to the hot cell interface | Movement | 0.18056
Remove vacuum pumping assembly | Move overhead crane to lower port | Movement | 0.22222
Install the divertor gauge rails | Move the test mass to the port interface | Movement | 0.18056
Correctness
Still being looked for
Adherence
Still being looked for

## Full_set_times
Group | Activity | Activity Type | Time | Cumulative Time (h) | Type | Equipment | Time (h) | Equipment | Start Location | End Location | Distance (m) | Speed (m/s) | Time (h) | Type | Time (h) | Activity | End | Slack
Survey hot cell and all in-cell equipment | Cassette Removal Required | Operation | 0 | 0 | Cassette Removal Required |  | 0 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Deploy in-cell inspection and handling system, and required tooling, into the hot cell | Logistics | 0.22 | 0.22 |  |  | N/A |  |  |  | N/A | N/A | N/A | Collect / desposit hardware from the hot cell interface | 0.22 |  | N/A | N/A
| Collect MPR from the hot cell interface | Logistics | 0.336 | 0.556 |  |  | N/A |  |  |  | N/A | N/A | N/A | Store / collect items with the overhead crane | 0.336 |  | N/A | N/A
| Move to the RM laydown area | Movement | 0.083333 | 0.63933 |  |  | N/A | Overhead crane (loaded) | Hot Cell Interface | RM equipment stillage | 6 | 0.02 | 0.083333 |  | N/A |  | N/A | N/A
| Place Multi-purpose robot (MPR) into RM laydown area | Logistics | 0.336 | 0.97533 |  |  | N/A |  |  |  | N/A | N/A | N/A | Store / collect items with the overhead crane | 0.336 |  | N/A | N/A
| Move overhead crane to hot cell interface | Movement | 0.0083333 | 0.98367 |  |  | N/A | Overhead crane (unloaded) | RM equipment Stillage | Hot cell interface | 6 | 0.2 | 0.0083333 |  | N/A |  | N/A | N/A
| Collect MPR tool storage | Logistics | 0.336 | 1.3197 |  |  | N/A |  |  |  | N/A | N/A | N/A | Store / collect items with the overhead crane | 0.336 |  | N/A | N/A
| Move to RM equipment laydown area | Movement | 0.083333 | 1.403 |  |  | N/A | Overhead crane (loaded) | Hot Cell Interface | RM equipment stillage | 6 | 0.02 | 0.083333 |  | N/A |  | N/A | N/A
| Install hot cell inspection tooling onto the MPR | Operation | 0.134 | 1.537 | Install and commission MPR tooling | MPR | 0.134 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Inspect all in-cell hardware | Operation | 2.0027 | 3.5397 | Inspect all Lower port hardware | MPR; | 2.0027 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Inspect structure of the hot cell | Operation | 8.9548 | 12.4945 | Inspect hot cell structure | MPR; | 8.9548 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Return to RM laydown area | Movement | 0.0026774 | 12.4972 |  |  | N/A | Multi-purpose robot (transport) | Lower Port | RM equipment stillage | 8 | 0.83 | 0.0026774 |  | N/A |  | N/A | N/A
Remove Bioshield Plug | Collect Bioshield door movers from hot cell interface | Logistics | 0.22 | 12.7172 |  |  | N/A |  |  |  | N/A | N/A | N/A | Collect / desposit hardware from the hot cell interface | 0.22 | Collect the bioshield door movers from storage and transfer into the hot cell | 0.11613 | 12.3811
| Move bioshield door movers to the bioshield door | Movement | 0.0043507 | 12.7215 |  |  | N/A | Multi-purpose robot (transport) | Hot Cell Interface | Lower Port | 13 | 0.83 | 0.0043507 |  | N/A |  | N/A | N/A
| Position bioshield movers | Logistics | 0.0492 | 12.7707 |  |  | N/A |  |  |  | N/A | N/A | N/A | Store / collect RM equipment from laydown area | 0.0492 |  | N/A | N/A
| Connect bioshield door movers service connectors and commission | Logistics | 0.6233 | 13.394 |  |  | N/A |  |  |  | N/A | N/A | N/A | Make and commission RM service connections | 0.6233 |  | N/A | N/A
| Open Lower Port bioshield door | Operation | 1.336 | 14.73 | Move Lower Port bioshield door | Bioshield door movers; | 1.336 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Disconnect bioshield door movers service connectors | Logistics | 0.188 | 14.918 |  |  | N/A |  |  |  | N/A | N/A | N/A | Disconnect RM services | 0.188 |  | N/A | N/A
Open the Vacuum Closure Plate door | Collect VCP handling frame door movers from hot cell interface | Logistics | 0.2126 | 15.1306 |  |  | N/A |  |  |  | N/A | N/A | N/A | Collect / store Equipment or Hardware in stillage | 0.2126 | Collect Vacuum closure plate handler and test mass from storage | 12.7755 | 2.1426
| Move test mass to lower port | Movement | 0.18056 | 15.3112 |  |  | N/A | Overhead crane (loaded) | Hot Cell Interface | Lower Port | 13 | 0.02 | 0.18056 |  | N/A |  | N/A | N/A
| Carry out commissioning tests of the VCP frame | Operation | 1.8678 | 17.179 | Install and inspect VCP hardware | VCP lifting frame; MPR | 1.8678 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Return test mass to storage location | Movement | 0.18056 | 17.3595 |  |  | N/A | Overhead crane (loaded) | Lower Port | Hot cell interface | 13 | 0.02 | 0.18056 |  | N/A |  | N/A | N/A
| Install and run VCP bolt runners | Operation | 1.6662 | 19.0257 | Install Lower Port VCP Autonomous bolt runners | MPR; VCP bolt runners | 1.6662 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Install and commission the VCP interface on to the handling frame | Operation | 1.8678 | 21.1413 | Install and inspect VCP hardware | MPR; VCP bolt runners | 1.8678 |  |  |  | N/A | N/A | N/A |  | N/A | Collect VCP handling frame from hot cell interface and move to port | 19.2735 | -0.24781
| Release VCP | Operation | 4.2662 | 25.4075 | Open VCP | VCP lifting frame; MPR | 4.2662 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Install vacuum sealing face protection and contamination control barriers | Operation | 1.7696 | 27.1771 | Install vacuum sealing face guards and contamination control barrier |  | 1.7696 |  |  |  | N/A | N/A | N/A |  | N/A | Collect VCP sealing face protection and contamination control system | 13.564 | 11.8435
Perform Health Physics and engineering checks | Move MPR into the port | Movement | 0.0043507 | 27.1814 |  |  | N/A | Multi-purpose robot (transport) | Hot Cell Interface | Lower Port | 13 | 0.83 | 0.0043507 |  | N/A |  | N/A | N/A
| Perform health physics checks | Operation | 3.7722 | 30.9537 | Perform Health Physics Checks | MPR; | 3.7722 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Perform engineering checks | Operation | 3.7722 | 34.7259 | Perform engineering checks | MPR; | 3.7722 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Return MPR to the RM laydown area | Movement | 0.0026774 | 34.7286 |  |  | N/A | Multi-purpose robot (transport) | Lower Port | RM equipment stillage | 8 | 0.83 | 0.0026774 | Recovery RM system from the port | N/A |  | N/A | N/A
Install threshold rails and in-port deployment system | Collect first set of threshold rails from the port interface | Logistics | 0.0492 | 34.7778 |  |  | N/A |  |  |  | N/A | N/A | N/A | Store / collect RM equipment from laydown area | 0.0492 | Move transporter to the RM long term store; collect first ex-vessel rails; move the hot cell interface | 21.7584 | 12.9702
| Move rails to the mouth of the port | Movement | 0.18056 | 34.9583 |  |  | N/A | Overhead crane (loaded) | Hot Cell Interface | Lower Port | 13 | 0.02 | 0.18056 |  | N/A |  | N/A | N/A
| Position rails using overhead crane | Logistics | 0.38 | 35.3383 |  |  | N/A |  |  |  | N/A | N/A | N/A | Reposition tool within Port | 0.38 |  | N/A | N/A
| Install Threshold rails | Operation | 2.3372 | 37.6755 | Install demountable port rails | MPR; | 2.3372 |  |  |  | N/A | N/A | N/A | Deploy RM system into the port | N/A |  | N/A | N/A
| Perform engineering checks | Operation | 3.7722 | 41.4478 | Perform engineering checks | MPR; | 3.7722 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Position second set of rails using overhead crane | Logistics | 0.38 | 41.8278 |  |  | N/A |  |  |  | N/A | N/A | N/A | Reposition tool within Port | 0.38 | Move transporter to the RM long term store; collect second ex-vessel rails; move rails into the hot cell | 35.6426 | 5.8051
| Install second threshold rail | Operation | 2.3372 | 44.165 | Install demountable port rails | MPR; | 2.3372 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Perform engineering checks | Operation | 3.7722 | 47.9372 | Perform engineering checks | MPR; | 3.7722 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Position second set of rails using overhead crane | Logistics | 0.38 | 48.3172 |  |  | N/A |  |  |  | N/A | N/A | N/A | Reposition tool within Port | 0.38 | Move transport to RM long term store; Collect IPD equipment; move to the lower port hot cell; collect the IPD with the overhead crane | 44.9626 | 2.9746
| Install the IPD | Operation | 3.7094 | 52.0266 | Install and commission the IPD chain and tractor | IPD; MPR | 3.7094 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Move test mass to the threshold rails | Movement | 0.11111 | 52.1377 |  |  | N/A | Overhead crane (loaded) | RM equipment Stillage | Lower Port | 8 | 0.02 | 0.11111 |  | N/A | Collect the test mass and move the lower port | 41.8881 | 10.1385
| Place test mass onto the threshold rails | Logistics | 0.0492 | 52.1869 |  |  | N/A |  |  |  | N/A | N/A | N/A | Store / collect RM equipment from laydown area | 0.0492 |  | N/A | N/A
| Couple the test mass to the IPD | Operation | 0.134 | 52.3209 | Couple / decouple IPD movers | MPR; | 0.134 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Load test the lower port rails and the IPD system | Operation | 2.786 | 55.1069 | Load test the IPD system | Test mass; IPD | 2.786 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Remove test mass from the port | Logistics | 0.0492 | 55.1561 |  |  | N/A |  |  |  | N/A | N/A | N/A | Store / collect RM equipment from laydown area | 0.0492 | Move transporter to long term RM store; collect robot arm stillage and vacuum pumping equipment; transport equipment into the lower port hot cell; transfer into the hot cell; Unload RM tools and equipment | 53.019 | 2.0879
| Decouple test mass from the IPD | Operation | 0.134 | 55.2901 | Couple / decouple IPD movers | MPR | 0.134 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Collect test mass with the overhead crane | Logistics | 0.0492 | 55.3393 |  |  | N/A |  |  |  | N/A | N/A | N/A | Store / collect RM equipment from laydown area | 0.0492 |  | N/A | N/A
| Move test mass back to the RM equipment stillage | Movement | 0.11111 | 55.4504 |  |  | N/A | Overhead crane (loaded) | Lower Port | RM equipment stillage | 8 | 0.02 | 0.11111 | Recovery RM system from the port | N/A |  | N/A | N/A
| Place test mass in laydown area | Logistics | 0.2126 | 55.663 |  |  | N/A |  |  |  | N/A | N/A | N/A | Collect / store Equipment or Hardware in stillage | 0.2126 |  | N/A | N/A
Remove vacuum pump service connection | Move overhead crane to the hot cell interface | Movement | 0.0083333 | 55.6713 |  |  | N/A | Overhead crane (unloaded) | RM equipment Stillage | Hot cell interface | 6 | 0.2 | 0.0083333 |  | N/A |  | N/A | N/A
| Collect IPD trailer | Logistics | 0.2126 | 55.8839 |  |  | N/A |  |  |  | N/A | N/A | N/A | Collect / store Equipment or Hardware in stillage | 0.2126 |  | N/A | N/A
| Move to lower port | Movement | 0.18056 | 56.0645 |  |  | N/A | Overhead crane (loaded) | Hot Cell Interface | Lower Port | 13 | 0.02 | 0.18056 |  | N/A |  | N/A | N/A
| Install IPD trailer equipment | Operation | 1.332 | 57.3965 | Install and commission the IPD trailer | MPR; | 1.332 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Move overhead crane to the RM robot arm storage | Movement | 0.022222 | 57.4187 |  |  | N/A | Overhead crane (unloaded) | Lower Port | RM robot arm storage | 16 | 0.2 | 0.022222 |  | N/A |  | N/A | N/A
| Collect dexterous robot arm from storage | Logistics | 0.2126 | 57.6313 |  |  | N/A |  |  |  | N/A | N/A | N/A | Collect / store Equipment or Hardware in stillage | 0.2126 |  | N/A | N/A
| Move to IPD trailer | Movement | 0.11111 | 57.7424 |  |  | N/A | Overhead crane (loaded) | RM equipment Stillage | Lower Port | 8 | 0.02 | 0.11111 |  | N/A |  | N/A | N/A
| Install dexterous arm onto the trailer | Operation | 2.332 | 60.0744 | Install and commission robot arm into an IPD mover | MPR; | 2.332 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Move MPR to RM tool storage | Movement | 0.0026774 | 60.0771 |  |  | N/A | Multi-purpose robot (transport) | Lower Port | RM equipment stillage | 8 | 0.83 | 0.0026774 |  | N/A |  | N/A | N/A
| Collect MPC actuation tooling | Logistics | 0.0492 | 60.1263 |  |  | N/A |  |  |  | N/A | N/A | N/A | Store / collect RM equipment from laydown area | 0.0492 |  | N/A | N/A
| Move to the lower port | Movement | 0.0026774 | 60.129 |  |  | N/A | Multi-purpose robot (transport) | RM equipment stillage | Lower Port | 8 | 0.83 | 0.0026774 |  | N/A |  | N/A | N/A
| Hand over to the IPD tractor | Logistics | 0.0492 | 60.1782 |  |  | N/A |  |  |  | N/A | N/A | N/A | Store / collect RM equipment from laydown area | 0.0492 |  | N/A | N/A
| Move IPD into the port | Movement | 0.0083333 | 60.1865 |  |  | N/A | In-port deployer (loaded) | Lower Port | Vacuum pumping equipment | 3 | 0.1 | 0.0083333 |  | N/A |  | N/A | N/A
| Install Mechanical pipe connection tooling to the first pipe module joint | Operation | 0.3056 | 60.4921 | Install Mechanical pipe connection tooling | Dexterous robot arm; MPC tooling | 0.3056 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Install Mechanical pipe connection tooling to the second pipe module joint | Operation | 0.3056 | 60.7977 | Install Mechanical pipe connection tooling | Dexterous robot arm; MPC tooling | 0.3056 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Release the first vacuum pump MPC | Operation | 0.1202 | 60.9179 | Actuate MPC tooling | MPC tooling | 0.1202 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Release the first vacuum pump MPC | Operation | 0.1202 | 61.0381 | Actuate MPC tooling | MPC tooling | 0.1202 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Collect pipe module using dexterous robot arm | Logistics | 0.2126 | 61.2507 |  |  | N/A |  |  |  | N/A | N/A | N/A | Collect / store Equipment or Hardware in stillage | 0.2126 |  | N/A | N/A
| Remove the pipe module from the port, using the IPD | Movement | 0.0083333 | 61.259 |  |  | N/A | In-port deployer (loaded) | Vacuum pumping equipment | Lower Port | 3 | 0.1 | 0.0083333 |  | N/A |  | N/A | N/A
| Place vacuum pump pipe module into a storage frame | Logistics | 0.2126 | 61.4716 |  |  | N/A |  |  |  | N/A | N/A | N/A | Collect / store Equipment or Hardware in stillage | 0.2126 | Move overhead crane over to the hot cell interface; collect CCB application system and pipe module storage frame; return to lower port | 60.8388 | 0.42025
| Install contamination control barrier | Operation | 0.1983 | 61.6699 | Install contamination control barrier | Overhead crane; CCB system | 0.1983 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Pick up the pipe module storage frame with the overhead crane | Logistics | 0.0492 | 61.7191 |  |  | N/A |  |  |  | N/A | N/A | N/A | Store / collect RM equipment from laydown area | 0.0492 |  | N/A | N/A
| Move the removed pipe module to the hot cell interface | Movement | 0.18056 | 61.8997 |  |  | N/A | Overhead crane (loaded) | Lower Port | Hot cell interface | 13 | 0.02 | 0.18056 |  | N/A |  | N/A | N/A
| Transfer vacuum pump pipe module to the port interface system | Logistics | 0.0492 | 61.9489 |  |  | N/A |  |  |  | N/A | N/A | N/A | Store / collect RM equipment from laydown area | 0.0492 |  | N/A | N/A
| Move overhead crane back to the upper port | Movement | 0.018056 | 61.9669 |  |  | N/A | Overhead crane (unloaded) | Hot Cell Interface | Lower Port | 13 | 0.2 | 0.018056 |  | N/A |  | N/A | N/A
| Decouple IPD trailer from IPD | Operation | 0.134 | 62.1009 | Couple / decouple IPD movers | MPR; IPD | 0.134 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Lift the IPD trailer from the threshold rails | Logistics | 0.0492 | 62.3032 |  |  | N/A |  |  |  | N/A | N/A | N/A | Store / collect RM equipment from laydown area | 0.0492 | Collect and Install vacuum pump service connection seals | 62.254 | -0.15309
| Move to RM tool storage laydown area | Movement | 0.027778 | 62.331 |  |  | N/A | Overhead crane (loaded) | Lower Port | RM tool storage | 2 | 0.02 | 0.027778 |  | N/A |  | N/A | N/A
| Store IPD trailer in the laydown area | Logistics | 0.0492 | 62.3802 |  |  | N/A |  |  |  | N/A | N/A | N/A | Store / collect RM equipment from laydown area | 0.0492 |  | N/A | N/A
Remove vacuum pumping assembly | Move overhead crane to hot cell interface | Movement | 0.013889 | 62.3941 |  |  | N/A | Overhead crane (unloaded) | RM tool storage | Hot cell interface | 10 | 0.2 | 0.013889 |  | N/A | Move transporter to RM tool storage; Collect vacuum pump transport system; transport to hot cell; transfer into hot cell | 56.0674 | 6.3128
| Collect robot arm lifting frame | Logistics | 0.0492 | 62.4433 |  |  | N/A |  |  |  | N/A | N/A | N/A | Store / collect RM equipment from laydown area | 0.0492 |  | N/A | N/A
| Collect high payload long reach robot arm from the storage frame | Logistics | 0.0492 | 62.4925 |  |  | N/A |  |  |  | N/A | N/A | N/A | Store / collect RM equipment from laydown area | 0.0492 |  | N/A | N/A
| Move overhead crane to lower port | Movement | 0.22222 | 62.7147 |  |  | N/A | Overhead crane (loaded) | RM robot arm storage | Lower Port | 16 | 0.02 | 0.22222 |  | N/A |  | N/A | N/A
| Install high payload robot arm on the IPD tractor | Operation | 2.332 | 65.0467 | Install and commission robot arm into an IPD mover | MPR; IPD | 2.332 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Move overhead crane to the port interface | Movement | 0.018056 | 65.0648 |  |  | N/A | Overhead crane (unloaded) | Lower Port | Hot cell interface | 13 | 0.2 | 0.018056 |  | N/A |  | N/A | N/A
| Collect Vacuum pump wheel jacks | Logistics | 0.0492 | 65.114 |  |  | N/A |  |  |  | N/A | N/A | N/A | Store / collect RM equipment from laydown area | 0.0492 |  | N/A | N/A
| Move to the RM tool storage area | Movement | 0.13889 | 65.2529 |  |  | N/A | Overhead crane (loaded) | Hot Cell Interface | RM tool storage | 10 | 0.02 | 0.13889 |  | N/A |  | N/A | N/A
| Place tool storage in laydown area | Logistics | 0.0492 | 65.3021 |  |  | N/A |  |  |  | N/A | N/A | N/A | Store / collect RM equipment from laydown area | 0.0492 |  | N/A | N/A
| Install Vacuum pump front wheel jacks | Operation | 1.002 | 66.3041 | Install Vacuum pump front wheel jacks | in-port rover | 1.002 |  |  |  | N/A | N/A | N/A |  | N/A | Move MPR to the hot cell interface; collect in-port rover; deliver to lower port | 62.4873 | 2.8148
| Install Vacuum pump rear wheel jacks | Operation | 0.86878 | 67.1729 | Install Vacuum pump rear wheel jacks | High payload robot arm | 0.86878 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Release Vacuum pump fixation tooling | Operation | 0.57211 | 67.745 | Release vacuum fixation tooling | High payload robot arm | 0.57211 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Move IPD tractor to the vacuum pump | Movement | 0.0083333 | 67.7533 |  |  | N/A | In-port deployer (loaded) | Lower Port | Vacuum pumping equipment | 3 | 0.1 | 0.0083333 |  | N/A |  | N/A | N/A
| Engage the IPD to the vacuum pumping assembly | Operation | 0.134 | 67.8873 | Couple / decouple IPD movers | Vacuum pump wheel jacks | 0.134 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Actuate vacuum pump fixation tooling | Operation | 0.102 | 67.9893 | Actuate vacuum pump wheel jacks | High payload robot arm | 0.102 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Withdraw pump assembly from the port | Movement | 0.0083333 | 67.9977 |  |  | N/A | In-port deployer (loaded) | Vacuum pumping equipment | Lower Port | 3 | 0.1 | 0.0083333 |  | N/A |  | N/A | N/A
| Release vacuum pump from the IPD | Logistics | 0.0492 | 68.0469 |  |  | N/A |  |  |  | N/A | N/A | N/A | Store / collect RM equipment from laydown area | 0.0492 |  | N/A | N/A
| Collect vaccum pump with the overhead crane | Logistics | 0.2126 | 68.2595 |  |  | N/A |  |  |  | N/A | N/A | N/A | Collect / store Equipment or Hardware in stillage | 0.2126 | Move overhead crane to port interface; collect vacuum pump contamination control barrier; move to lower port | 65.7399 | 2.3069
| Apply vacuum pump contamination control barrier | Operation | 0.1983 | 68.4578 | Install contamination control barrier | Overhead crane; CCB system | 0.1983 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Move vacuum pump to PP hardware laydown area | Movement | 0.13889 | 68.5966 |  |  | N/A | Overhead crane (loaded) | Lower Port | PP hardware stillage | 10 | 0.02 | 0.13889 |  | N/A |  | N/A | N/A
| Deposit vacuum pump in the storage frame | Logistics | 0.2126 | 68.8092 |  |  | N/A |  |  |  | N/A | N/A | N/A | Collect / store Equipment or Hardware in stillage | 0.2126 |  | N/A | N/A
| Move crane to RM tool storage | Movement | 0.011111 | 68.8204 |  |  | N/A | Overhead crane (unloaded) | PP hardware stillage | RM tool storage | 8 | 0.2 | 0.011111 |  | N/A |  | N/A | N/A
| Collect vacuum pump RM tool storage | Logistics | 0.0492 | 68.8696 |  |  | N/A |  |  |  | N/A | N/A | N/A | Store / collect RM equipment from laydown area | 0.0492 |  | N/A | N/A
| Move to hot cell interface | Movement | 0.13889 | 69.0084 |  |  | N/A | Overhead crane (loaded) | RM tool storage | Hot cell interface | 10 | 0.02 | 0.13889 |  | N/A |  | N/A | N/A
| Deposit RM tool storage | Logistics | 0.0492 | 69.0576 |  |  | N/A |  |  |  | N/A | N/A | N/A | Store / collect RM equipment from laydown area | 0.0492 |  | N/A | N/A
Inspection revealed in-port area | Move inspection tooling into the port | Movement | 0.0083333 | 69.066 |  |  | N/A | In-port deployer (loaded) | Lower Port | Vacuum pumping equipment | 3 | 0.1 | 0.0083333 |  | N/A | Collect in-port inspection system from RM tool storage; move to lower port; install and commission on long reach robot arm | 68.525 | 0.53263
| Inspect revealed port liner | Operation | 0.36361 | 69.4296 | Inspect revealed area of the lower port | Long reach robot arm | 0.36361 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Remove inspection system from the port | Movement | 0.036111 | 69.4657 |  |  | N/A | In-port deployer (loaded) | Vacuum pumping equipment | RM tool storage | 13 | 0.1 | 0.036111 |  | N/A |  | N/A | N/A
| Return inspection tooling to RM storage | Logistics | 0.0492 | 69.5149 |  |  | N/A |  |  |  | N/A | N/A | N/A | Store / collect RM equipment from laydown area | 0.0492 |  | N/A | N/A
| Return IPD tractor to the lower port interface | Movement | 0.0055556 | 69.5205 |  |  | N/A | In-port deployer (loaded) | RM tool storage | Lower Port | 2 | 0.1 | 0.0055556 |  | N/A |  | N/A | N/A
Install the divertor gauge rails | Collect divertor gauge rails from the hot cell interface | Logistics | 0.0492 | 69.5697 |  |  | N/A |  |  |  | N/A | N/A | N/A | Store / collect RM equipment from laydown area | 0.0492 | Collect divertor gauge rails from stores; move into the hot cell; collect with the overhead crane; move to lower port | 62.963 | 6.5574
| Transport rails to the lower port interface | Movement | 0.18056 | 69.7502 |  |  | N/A | Overhead crane (loaded) | Hot Cell Interface | Lower Port | 13 | 0.02 | 0.18056 |  | N/A |  | N/A | N/A
| Place divertor gauge rails onto the threshold rails | Logistics | 0.0492 | 69.7994 |  |  | N/A |  |  |  | N/A | N/A | N/A | Store / collect RM equipment from laydown area | 0.0492 |  | N/A | N/A
| Collect the rails using the IPD tractor | Logistics | 0.0492 | 69.8486 |  |  | N/A |  |  |  | N/A | N/A | N/A | Store / collect RM equipment from laydown area | 0.0492 |  | N/A | N/A
| Transfer the rails to the end of the horizontal port | Movement | 0.022222 | 69.8708 |  |  | N/A | In-port deployer (loaded) | Lower Port | Divertor pipe modules | 8 | 0.1 | 0.022222 |  | N/A |  | N/A | N/A
| Install the divertor gauge rails | Operation | 2.3372 | 72.2081 | Install demountable port rails | Long reach robot arm | 2.3372 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Disconnect the rails from the IPD tractor | Logistics | 0.0492 | 72.2573 |  |  | N/A |  |  |  | N/A | N/A | N/A | Store / collect RM equipment from laydown area | 0.0492 |  | N/A | N/A
| Remove IPD tractor from the port | Movement | 0.022222 | 72.2795 |  |  | N/A | In-port deployer (loaded) | Divertor pipe modules | Lower Port | 8 | 0.1 | 0.022222 |  | N/A |  | N/A | N/A
| Place test mass onto the threshold rails | Logistics | 0.0492 | 72.3287 |  |  | N/A |  |  |  | N/A | N/A | N/A | Store / collect RM equipment from laydown area | 0.0492 | Move the overhead crane to the RM equipment stillage; collect test mass from laydown area; move to the lower port | 69.9708 | 2.3086
| Connect to the IPD tractor | Operation | 0.134 | 72.4627 | Couple / decouple IPD movers | MPR | 0.134 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Move test mass onto the port rails | Movement | 0.022222 | 72.4849 |  |  | N/A | In-port deployer (loaded) | Lower Port | Divertor pipe modules | 8 | 0.1 | 0.022222 |  | N/A |  | N/A | N/A
| Load test the divertor port rails | Operation | 2.786 | 75.2709 | Load test the IPD system | Test mass; IPD | 2.786 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Recover the test mass from the inport | Movement | 0.022222 | 75.2931 |  |  | N/A | In-port deployer (loaded) | Divertor pipe modules | Lower Port | 8 | 0.1 | 0.022222 |  | N/A |  | N/A | N/A
| Decouple the test mass from the IPD | Operation | 0.134 | 75.4271 | Couple / decouple IPD movers |  | 0.134 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Collect the test mass with the overhead crane | Logistics | 0.0492 | 75.4763 |  |  | N/A |  |  |  | N/A | N/A | N/A | Store / collect RM equipment from laydown area | 0.0492 |  | N/A | N/A
| Move the test mass to the port interface | Movement | 0.18056 | 75.6569 |  |  | N/A | Overhead crane (loaded) | Lower Port | Hot cell interface | 13 | 0.02 | 0.18056 |  | N/A |  | N/A | N/A
| Transfer the test mass to the port interface | Logistics | 0.0492 | 75.7061 |  |  | N/A |  |  |  | N/A | N/A | N/A | Store / collect RM equipment from laydown area | 0.0492 |  | N/A | N/A
Install and commission divertor pipework handling equipment | Move arm to robot arm storage | Movement | 0.0027778 | 75.7089 |  |  | N/A | Overhead crane (unloaded) | Hot Cell Interface | RM robot arm storage | 2 | 0.2 | 0.0027778 |  | N/A |  | N/A | N/A
| Collect robot arm lifting frame | Logistics | 0.0492 | 75.7581 |  |  | N/A |  |  |  | N/A | N/A | N/A | Store / collect RM equipment from laydown area | 0.0492 |  | N/A | N/A
| Move overhead crane to the lower port | Movement | 0.018056 | 75.7761 |  |  | N/A | Overhead crane (unloaded) | Hot Cell Interface | Lower Port | 13 | 0.2 | 0.018056 |  | N/A | Move transporter to long term RM store; collect divertor pipe handling equipment; return to the hot cell interface; transfer hardware into the hot cell | 70.1867 | 5.5713
| Remove high payload arm off the IPD tractor | Operation | 0.418 | 76.1941 | Remove robot arm from the IPD | Overhead crane; MPR; IPD | 0.418 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Transport the robot arm to the RM robot arm storage area | Movement | 0.22222 | 76.4163 |  |  | N/A | Overhead crane (loaded) | Lower Port | RM robot arm storage | 16 | 0.02 | 0.22222 |  | N/A |  | N/A | N/A
| Store the long reach high payload arm | Logistics | 0.0492 | 76.4655 |  |  | N/A |  |  |  | N/A | N/A | N/A | Store / collect RM equipment from laydown area | 0.0492 |  | N/A | N/A
| Move overhead crane to the IPD tractor | Movement | 0.22222 | 76.6878 |  |  | N/A | Overhead crane (loaded) | RM robot arm storage | Lower Port | 16 | 0.02 | 0.22222 | Store / collect RM equipment from laydown area | N/A |  | N/A | N/A
| Install and commission the dexterous arm on the IPD tractor | Operation | 2.332 | 79.0198 | Install and commission robot arm into an IPD mover | MPR; IPD; long reach robot arm | 2.332 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Move the overhead crane to RM equipment storage | Movement | 0.11111 | 79.1309 |  |  | N/A | Overhead crane (loaded) | Lower Port | RM equipment stillage | 8 | 0.02 | 0.11111 |  | N/A |  | N/A | N/A
| Collect IPD trailer from storage | Logistics | 0.0492 | 79.1801 |  |  | N/A |  |  |  | N/A | N/A | N/A | Store / collect RM equipment from laydown area | 0.0492 |  | N/A | N/A
| Move to lower port | Movement | 0.11111 | 79.2912 |  |  | N/A | Overhead crane (loaded) | RM equipment stillage | Lower Port | 8 | 0.02 | 0.11111 |  | N/A |  | N/A | N/A
| Install and commssion the IPD trailer on the port rails | Operation | 1.332 | 80.6232 | Install and commission the IPD trailer | IPD; MPR | 1.332 |  |  |  | N/A | N/A | N/A | Reposition tool within Port | N/A |  | N/A | N/A
| Move overhead crane to the RM tool storage | Movement | 0.022222 | 80.6454 |  |  | N/A | Overhead crane (unloaded) | Lower Port | RM robot arm storage | 16 | 0.2 | 0.022222 |  | N/A |  | N/A | N/A
| Store robot arm lifting frame | Logistics | 0.2126 | 80.858 |  |  | N/A |  |  |  | N/A | N/A | N/A | Collect / store Equipment or hardware in stillage | 0.2126 |  | N/A | N/A
| Move overhead crane to the port interface | Movement | 0.0027778 | 80.8608 |  |  | N/A | Overhead crane (unloaded) | RM robot arm storage | Hot cell interface | 2 | 0.2 | 0.0027778 |  | N/A |  | N/A | N/A
| Collect pipe module handler | Logistics | 0.0492 | 80.91 |  |  | N/A |  |  |  | N/A | N/A | N/A | Store / collect RM equipment from laydown area | 0.0492 |  | N/A | N/A
| Move to the lower port | Movement | 0.18056 | 81.0905 |  |  | N/A | Overhead crane (loaded) | Hot Cell Interface | Lower Port | 13 | 0.02 | 0.18056 |  | N/A |  | N/A | N/A
| Install and commission the divertor pipe module handler | Operation | 1.332 | 82.4225 | Install and commission the IPD trailer | IPD; MPR | 1.332 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Move overhead crane to the hot cell interface | Movement | 0.018056 | 82.4406 |  |  | N/A | Overhead crane (unloaded) | Lower Port | Hot cell interface | 13 | 0.2 | 0.018056 |  | N/A |  | N/A | N/A
| Collect divertor pipework tool storage | Logistics | 0.0492 | 82.4898 |  |  | N/A |  |  |  | N/A | N/A | N/A | Store / collect RM equipment from laydown area | 0.0492 |  | N/A | N/A
| Transport divertor tool storage to the RM tool storeage location | Movement | 0.13889 | 82.6287 |  |  | N/A | Overhead crane (loaded) | Hot Cell Interface | RM tool storage | 10 | 0.02 | 0.13889 |  | N/A |  | N/A | N/A
| Deposit divertor pipework tools in laydown area | Logistics | 0.0492 | 82.6779 |  |  | N/A |  |  |  | N/A | N/A | N/A | Store / collect RM equipment from laydown area | 0.0492 |  | N/A | N/A
| Transfer the collected SJS cable pully to the IPD tractor | Logistics | 0.0492 | 82.7271 |  |  | N/A |  |  |  | N/A | N/A | N/A | Store / collect RM equipment from laydown area | 0.0492 | Collect the SJS pully with the MPR; transfer to the IPD | 82.4794 | 0.19845
Commission the SJS services cask and associate hardware | Transport SJS services cask from the hot cell interface | Movement | 0.083333 | 82.8104 |  |  | N/A | Overhead crane (loaded) | Hot Cell Interface | RM equipment stillage | 6 | 0.02 | 0.083333 |  | N/A | Collect the SJS services cask from the hot cell interface; move to the RM laydown area | 82.6918 | 0.035311
| Deposit the SJS services cask in the laydown area | Logistics | 0.0492 | 82.8596 |  |  | N/A |  |  |  | N/A | N/A | N/A | Store / collect RM equipment from laydown area | 0.0492 |  | N/A | N/A
| Move MPR to the SJS service cask | Movement | 0.0016734 | 82.8613 |  |  | N/A | Multi-purpose robot (transport) | RM tool storage | RM equipment stillage | 5 | 0.83 | 0.0016734 |  | N/A |  | N/A | N/A
| Collect SJS deployment system from the SJS cask | Logistics | 0.362 | 83.2233 |  |  | N/A |  |  |  | N/A | N/A | N/A | Deploy / recover RM tools | 0.362 |  | N/A | N/A
| Move the MRP to the RM tool storage area | Movement | 0.0016734 | 83.225 |  |  | N/A | Multi-purpose robot (transport) | RM equipment stillage | RM tool storage | 5 | 0.83 | 0.0016734 |  | N/A |  | N/A | N/A
| Transfer the SJS deployment system to the IPD robot arm | Logistics | 0.362 | 83.587 |  |  | N/A |  |  |  | N/A | N/A | N/A | Deploy / recover RM tools | 0.362 |  | N/A | N/A
| Collect MPC actuation tooling from tool storage | Logistics | 0.0492 | 83.6362 |  |  | N/A |  |  |  | N/A | N/A | N/A | Store / collect RM equipment from laydown area | 0.0492 |  | N/A | N/A
| Transfer MPC actiation tooling to the IPD | Logistics | 0.0492 | 83.6854 |  |  | N/A |  |  |  | N/A | N/A | N/A | Store / collect RM equipment from laydown area | 0.0492 |  | N/A | N/A
| Collect service connection seal from tool storage | Logistics | 0.0492 | 83.7346 |  |  | N/A |  |  |  | N/A | N/A | N/A | Store / collect RM equipment from laydown area | 0.0492 |  | N/A | N/A
| Transfer service connection seal to the IPD | Logistics | 0.0492 | 83.7838 |  |  | N/A |  |  |  | N/A | N/A | N/A | Store / collect RM equipment from laydown area | 0.0492 |  | N/A | N/A
| Move the IPD train into the port | Movement | 0.0083333 | 83.7921 |  |  | N/A | In-port deployer (loaded) | Lower Port | Vacuum pumping equipment | 3 | 0.1 | 0.0083333 |  | N/A |  | N/A | N/A
| Install the SJS pulley into the side of the port and commission | Operation | 0.516 | 84.3081 | Install SJS pulley system | High payload robot arm | 0.516 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
Remove Central Divetor pipe module | Move the IPD to the divetor pipe modules | Movement | 0.0055556 | 84.3136 |  |  | N/A | In-port deployer (loaded) | Vacuum pumping equipment | Divertor pipe modules | 2 | 0.1 | 0.0055556 |  | N/A |  | N/A | N/A
| Position the pipe module handler onto the pipe module | Logistics | 0.38 | 84.6936 |  |  | N/A |  |  |  | N/A | N/A | N/A | Reposition tool within Port | 0.38 |  | N/A | N/A
| Store SJS deployment system onto port storage location | Logistics | 0.362 | 85.0556 |  |  | N/A |  |  |  | N/A | N/A | N/A | Deploy / recover RM tools | 0.362 |  | N/A | N/A
| Install MPC actuation tooling | Operation | 0.3056 | 85.3612 | Install Mechanical pipe connection tooling | high payload robot arm; MPC tooling | 0.3056 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Remove pipe module access cover | Operation | 2.01 | 87.3712 | Remove divertor pipe module access cover | Dexterous robot arm; MPC tooling | 2.01 |  |  |  | N/A | N/A | N/A | Recover Tool / Hardware from the Port | N/A |  | N/A | N/A
| Store removed access cover | Logistics | 0.0492 | 87.4204 |  |  | N/A |  |  |  | N/A | N/A | N/A | Store / collect RM equipment from laydown area | 0.0492 |  | N/A | N/A
| Collect pipe inspection tooling | Logistics | 0.362 | 87.7824 |  |  | N/A |  |  |  | N/A | N/A | N/A | Deploy / recover RM tools | 0.362 |  | N/A | N/A
| Inspect divetor pipework | Operation | 2.112 | 89.8944 | Inspect divertor pipe in-bore and pipe module interface | Dexterous robot arm | 2.112 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Collect SJS deployment system from the storage location | Logistics | 0.6 | 90.4944 |  |  | N/A |  |  |  | N/A | N/A | N/A | Recover Tool / Hardware from the Port | 0.6 |  | N/A | N/A
| Release divertor pipe module mechanical pipe connection | Operation | 0.1202 | 90.6146 | Actuate MPC tooling | MPC tooling | 0.1202 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Disconnect divertor pipe module from the divertor cassette | Operation | 1.1026 | 91.7173 | Disconnect divertor pipe module | outboard pipe module handler; SJS cutting system | 1.1026 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Replace SJS into storage location | Logistics | 0.362 | 92.0793 |  |  | N/A |  |  |  | N/A | N/A | N/A | Deploy / recover RM tools | 0.362 |  | N/A | N/A
| Reposition high layload arm to support the divertor pipe module | Logistics | 0.38 | 92.4593 |  |  | N/A |  |  |  | N/A | N/A | N/A | Reposition tool within Port | 0.38 |  | N/A | N/A
| Engage pipe module handling fixations | Operation | 0.0243 | 92.4836 | Actuate handling interfaces | Dexterous robot arm | 0.0243 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Reposition dexterous robot arm to release pipe module fixations | Logistics | 0.38 | 92.8636 |  |  | N/A |  |  |  | N/A | N/A | N/A | Reposition tool within Port | 0.38 |  | N/A | N/A
| Release divertor pipe module fixations | Operation | 0.118 | 92.9816 | Release lower port pipe module from the port fixations | pipe module handler; high payload robot arm | 0.118 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Remove the pipe module from the port, using the IPD | Operation | 3 | 95.9816 | Remove pipe module from the port | pipe module handler; high payload robot arm | 3 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Collect the pipe module using the overhead crane | Logistics | 0.0492 | 96.0308 |  |  | N/A |  |  |  | N/A | N/A | N/A | Store / collect RM equipment from laydown area | 0.0492 | Move ex-vessel transporter to PP store; Collect central Divertor pipe module cask; move cask into hot cell | 83.5909 | 12.3907
| Release the central divertor pipe module from the robot arm | Logistics | 0.0492 | 96.08 |  |  | N/A |  |  |  | N/A | N/A | N/A | Store / collect RM equipment from laydown area | 0.0492 |  | N/A | N/A
Remove Left Divetor pipe module | Move the IPD to the divetor pipe modules | Movement | 0.0055556 | 96.0855 |  |  | N/A | In-port deployer (loaded) | Vacuum pumping equipment | Divertor pipe modules | 2 | 0.1 | 0.0055556 |  | N/A |  | N/A | N/A
| Collect service connection seal from IPD | Logistics | 0.0492 | 96.1347 |  |  | N/A |  |  |  | N/A | N/A | N/A | Store / collect RM equipment from laydown area | 0.0492 |  | N/A | N/A
| Install service connection seal | Operation | 0.0403 | 96.175 | Install / remove MPC seals | Dexterous robot arm; MPC tooling | 0.0403 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Actuate MPC tooling to seal pipe stub | Operation | 0.1202 | 96.2952 | Actuate MPC tooling | MPC tooling | 0.1202 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Remove MPC tooling from central pipe module location | Operation | 0.1233 | 96.4185 | Remove MPC tooling | Dexterous robot arm; MPC tooling | 0.1233 |  |  |  | N/A | N/A | N/A | Reposition tool within Port | N/A |  | N/A | N/A
| Install MPC actuation tooling on the left divertor pipe module | Operation | 0.3056 | 96.7241 | Install Mechanical pipe connection tooling | MPC tooling | 0.3056 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Remove pipe module access cover | Operation | 2.01 | 98.7341 | Remove divertor pipe module access cover | Dexterous robot arm | 2.01 |  |  |  | N/A | N/A | N/A | Recover Tool / Hardware from the Port | N/A |  | N/A | N/A
| Store removed access cover | Logistics | 0.0492 | 98.7833 |  |  | N/A |  |  |  | N/A | N/A | N/A | Store / collect RM equipment from laydown area | 0.0492 |  | N/A | N/A
| Collect pipe inspection tooling | Logistics | 0.362 | 99.1453 |  |  | N/A |  |  |  | N/A | N/A | N/A | Deploy / recover RM tools | 0.362 |  | N/A | N/A
| Inspect divetor pipework | Operation | 2.112 | 101.2573 | Inspect divertor pipe in-bore and pipe module interface | Dexterous robot arm | 2.112 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Collect SJS deployment system from the storage location | Logistics | 0.6 | 101.8573 |  |  | N/A |  |  |  | N/A | N/A | N/A | Recover Tool / Hardware from the Port | 0.6 |  | N/A | N/A
| Release divertor pipe module mechanical pipe connection | Operation | 0.1202 | 101.9775 | Actuate MPC tooling |  | 0.1202 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Disconnect divertor pipe module from the divertor cassette | Operation | 1.1026 | 103.0801 | Disconnect divertor pipe module | outboard pipe module handler; SJS cutting system | 1.1026 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Reposition high layload arm to support the divertor pipe module | Logistics | 0.38 | 103.4601 |  |  | N/A |  |  |  | N/A | N/A | N/A | Reposition tool within Port | 0.38 |  | N/A | N/A
| Replace SJS into storage location | Logistics | 0.362 | 103.8221 |  |  | N/A |  |  |  | N/A | N/A | N/A | Deploy / recover RM tools | 0.362 |  | N/A | N/A
| Engage pipe module handling fixations | Operation | 0.0243 | 103.8464 | Actuate handling interfaces | Dexterous robot arm | 0.0243 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Reposition dexterous robot arm to release pipe module fixations | Logistics | 0.38 | 104.2264 |  |  | N/A |  |  |  | N/A | N/A | N/A | Reposition tool within Port | 0.38 |  | N/A | N/A
| Release divertor pipe module fixations | Operation | 0.118 | 104.3444 | Release lower port pipe module from the port fixations | pipe module handler; high payload robot arm | 0.118 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Remove the pipe module from the port, using the IPD | Operation | 3 | 107.3444 | Remove pipe module from the port | pipe module handler; high payload robot arm | 3 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Collect the left divertor pipe module using the overhead crane | Logistics | 0.0492 | 107.3936 |  |  | N/A |  |  |  | N/A | N/A | N/A | Store / collect RM equipment from laydown area | 0.0492 |  | N/A | N/A
| Release the left divertor pipe module from the robot arm | Logistics | 0.0492 | 107.4428 |  |  | N/A |  |  |  | N/A | N/A | N/A | Store / collect RM equipment from laydown area | 0.0492 | Collect central divertor pipe module from the IPD; store in transport cask; move to long term PP hardware storage; Collect new cask; transport into the hot cell | 97.5517 | 9.8419
Remove Right Divetor pipe module | Move the IPD to the divetor pipe modules | Movement | 0.0055556 | 107.4484 |  |  | N/A | In-port deployer (loaded) | Vacuum pumping equipment | Divertor pipe modules | 2 | 0.1 | 0.0055556 |  | N/A |  | N/A | N/A
| Position the pipe module handler onto the pipe module | Logistics | 0.38 | 107.8284 |  |  | N/A |  |  |  | N/A | N/A | N/A | Reposition tool within Port | 0.38 |  | N/A | N/A
| Collect service connection seal from IPD | Logistics | 0.0492 | 107.8776 |  |  | N/A |  |  |  | N/A | N/A | N/A | Store / collect RM equipment from laydown area | 0.0492 |  | N/A | N/A
| Install service connection seal | Operation | 0.0403 | 107.9179 | Install / remove MPC seals | Dexterous robot arm; MPC tooling | 0.0403 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Actuate MPC tooling to seal pipe stub | Operation | 0.1202 | 108.0381 | Actuate MPC tooling | MPC tooling | 0.1202 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Remove MPC tooling from central pipe module location | Operation | 0.1233 | 108.1614 | Remove MPC tooling | Dexterous robot arm; MPC tooling | 0.1233 |  |  |  | N/A | N/A | N/A | Reposition tool within Port | N/A |  | N/A | N/A
| Install MPC actuation tooling | Operation | 0.3056 | 108.467 | Install Mechanical pipe connection tooling | MPC tooling | 0.3056 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Remove pipe module access cover | Operation | 2.01 | 110.477 | Remove divertor pipe module access cover | Dexterous robot arm | 2.01 |  |  |  | N/A | N/A | N/A | Recover Tool / Hardware from the Port | N/A |  | N/A | N/A
| Store removed access cover | Logistics | 0.0492 | 110.5262 |  |  | N/A |  |  |  | N/A | N/A | N/A | Store / collect RM equipment from laydown area | 0.0492 |  | N/A | N/A
| Collect pipe inspection tooling | Logistics | 0.362 | 110.8882 |  |  | N/A |  |  |  | N/A | N/A | N/A | Deploy / recover RM tools | 0.362 |  | N/A | N/A
| Inspect divetor pipework | Operation | 2.112 | 113.0002 | Inspect divertor pipe in-bore and pipe module interface | Dexterous robot arm | 2.112 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Collect SJS deployment system from the storage location | Logistics | 0.6 | 113.6002 |  |  | N/A |  |  |  | N/A | N/A | N/A | Recover Tool / Hardware from the Port | 0.6 |  | N/A | N/A
| Release divertor pipe module mechanical pipe connection | Operation | 0.1202 | 113.7204 | Actuate MPC tooling |  | 0.1202 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Disconnect divertor pipe module from the divertor cassette | Operation | 1.1026 | 114.823 | Disconnect divertor pipe module | outboard pipe module handler; SJS cutting system | 1.1026 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Replace SJS into storage location | Logistics | 0.362 | 115.185 |  |  | N/A |  |  |  | N/A | N/A | N/A | Deploy / recover RM tools | 0.362 |  | N/A | N/A
| Reposition high layload arm to support the divertor pipe module | Logistics | 0.38 | 115.565 |  |  | N/A |  |  |  | N/A | N/A | N/A | Reposition tool within Port | 0.38 |  | N/A | N/A
| Engage pipe module handling fixations | Operation | 0.0243 | 115.5893 | Actuate handling interfaces | Dexterous robot arm | 0.0243 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Reposition dexterous robot arm to release pipe module fixations | Logistics | 0.38 | 115.9693 |  |  | N/A |  |  |  | N/A | N/A | N/A | Reposition tool within Port | 0.38 |  | N/A | N/A
| Release divertor pipe module fixations | Operation | 0.118 | 116.0873 | Release lower port pipe module from the port fixations | pipe module handler; high payload robot arm | 0.118 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Remove theright divertor pipe module from the port, using the IPD | Operation | 3 | 119.0873 | Remove pipe module from the port | pipe module handler; high payload robot arm | 3 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Collect the right divertor pipe module using the overhead crane | Logistics | 0.0492 | 119.1365 |  |  | N/A |  |  |  | N/A | N/A | N/A | Store / collect RM equipment from laydown area | 0.0492 |  | N/A | N/A
| Release the right divertor pipe module from the robot arm | Logistics | 0.0492 | 119.1857 |  |  | N/A |  |  |  | N/A | N/A | N/A | Store / collect RM equipment from laydown area | 0.0492 |  | N/A | N/A
| Move overhead crane from lower port to the hot cell interface | Movement | 0.18056 | 119.3663 |  |  | N/A | Overhead crane (loaded) | Lower port | Hot Cell Interface | 13 | 0.02 | 0.18056 |  | N/A |  | N/A | N/A
| Place divertor pipe module into the transport cask | Logistics | 0.2126 | 119.5789 |  |  | N/A |  |  |  | N/A | N/A | N/A | Collect / store Equipment or Hardware in stillage | 0.2126 | Collect left divertor pipe module from the IPD; store in transport cask; move to long term PP hardware storage; Collect new cask; transport into the hot cell | 108.8654 | 10.5009
Remove divertor pipe module handler and commission divertor handler | Move overhead crane to the lower port interface | Movement | 0.018056 | 119.5969 |  |  | N/A | Overhead crane (unloaded) | Hot Cell Interface | Lower Port | 13 | 0.2 | 0.018056 |  | N/A | Move MPR from storage location to lower port; decouple pipe module handler from IPD | 119.224 | 0.35488
| Collect pipe module handler from the IPD | Logistics | 0.0492 | 119.6461 |  |  | N/A |  |  |  | N/A | N/A | N/A | Store / collect RM equipment from laydown area | 0.0492 |  | N/A | N/A
| Move crane to the the RM equipment laydown area | Movement | 0.11111 | 119.7572 |  |  | N/A | Overhead crane (loaded) | Lower port | RM equipment stillage | 8 | 0.02 | 0.11111 |  | N/A |  | N/A | N/A
| Deposit the pipe module handler on the hot cell interface | Logistics | 0.0492 | 119.8064 |  |  | N/A |  |  |  | N/A | N/A | N/A | Store / collect RM equipment from laydown area | 0.0492 |  | N/A | N/A
| Move the overhead crane to collect the hot cell inerface | Movement | 0.11111 | 119.9175 |  |  | N/A | Overhead crane (loaded) | Lower port | RM equipment stillage | 8 | 0.02 | 0.11111 |  | N/A |  | N/A | N/A
| Collect divertor cassette from the hot cell interface | Logistics | 0.0492 | 120.7913 |  |  | N/A |  |  |  | N/A | N/A | N/A | Store / collect RM equipment from laydown area | 0.0492 | Collect collect right divertor pipe module; deposite in the PP stores; move the RM equipment stores; collect divertor cassette handler; move to port interface; transfer into the port | 120.7421 | -0.82456
| Move cassette handler to the lower port | Movement | 0.18056 | 120.9719 |  |  | N/A | Overhead crane (loaded) | Hot Cell Interface | Lower Port | 13 | 0.02 | 0.18056 |  | N/A |  | N/A | N/A
| Place divertor cassette handler onto the threshold rails | Logistics | 0.0492 | 121.0211 |  |  | N/A |  |  |  | N/A | N/A | N/A | Store / collect RM equipment from laydown area | 0.0492 |  | N/A | N/A
| Commission the divertor cassette handler | Operation | 1.332 | 122.3531 | Install and commission the IPD trailer | MPR; IPD; divertor cassette handler | 1.332 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
Remove Centre Divertor Cassette | Transport the divertor cassette mover to the divertor cassettes | Movement | 0.036111 | 122.3892 |  |  | N/A | In-port deployer (loaded) | Lower port | Divertor cassettes | 13 | 0.1 | 0.036111 | Deploy / recover RM tools | N/A |  | N/A | N/A
| Remove the central divertor cassette | Operation | 1.144 | 123.5332 | Remove Centre Divertor Cassette | IPD; divertor cassette handler | 1.144 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Transport removed cassette to the lower port interface | Movement | 0.036111 | 123.5693 |  |  | N/A | In-port deployer (loaded) | Divertor cassettes | Lower Port | 13 | 0.1 | 0.036111 |  | N/A |  | N/A | N/A
| Collect divertor cassette from the IPD | Logistics | 0.2126 | 123.7819 |  |  | N/A |  |  |  | N/A | N/A | N/A | Collect / store Equipment or Hardware in stillage | 0.2126 | Move ex-vessel transporter to RM equipment store; collect divertor cassette transport frame and CCB; transfer equipment into the hot cell | 121.6457 | 1.9236
| Move cassette to the transport frame | Movement | 0.027778 | 123.8097 |  |  | N/A | Overhead crane (loaded) | Lower port | RM tool storage | 2 | 0.02 | 0.027778 |  | N/A |  | N/A | N/A
| Install centre cassette into the transport frame | Logistics | 0.2126 | 124.0223 |  |  | N/A |  |  |  | N/A | N/A | N/A | Collect / store Equipment or Hardware in stillage | 0.2126 |  | N/A | N/A
Remove Left Divertor Cassette | Transport the divertor cassette mover to the divertor cassettes | Movement | 0.036111 | 124.0584 |  |  | N/A | In-port deployer (loaded) | Lower port | Divertor cassettes | 13 | 0.1 | 0.036111 | Deploy / recover RM tools | N/A |  | N/A | N/A
| Remove the left divertor cassette | Operation | 1.412 | 125.4704 | Remove Lateral Divertor Cassette | IPD; divertor cassette handler | 1.412 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Transport removed cassette to the lower port interface | Movement | 0.036111 | 125.5065 |  |  | N/A | In-port deployer (loaded) | Divertor cassettes | Lower Port | 13 | 0.1 | 0.036111 |  | N/A |  | N/A | N/A
| Collect divertor cassette from the IPD | Logistics | 0.2126 | 126.0178 |  |  | N/A |  |  |  | N/A | N/A | N/A | Collect / store Equipment or Hardware in stillage | 0.2126 | Move overhead crane to hot cell interface; collect centre div cassette CCB system; move to lower port; collect centre div cassette; transport to long term store; collect new handling system; transport to lower port | 125.8052 | -0.29868
| Move cassette to the transport frame | Movement | 0.027778 | 126.0455 |  |  | N/A | Overhead crane (loaded) | Lower port | RM tool storage | 2 | 0.02 | 0.027778 |  | N/A |  | N/A | N/A
| Install left cassette into the transport frame | Logistics | 0.2126 | 126.2581 |  |  | N/A |  |  |  | N/A | N/A | N/A | Collect / store Equipment or Hardware in stillage | 0.2126 |  | N/A | N/A
Remove Right Divertor Cassette | Transport the divertor cassette mover to the divertor cassettes | Movement | 0.036111 | 126.2943 |  |  | N/A | In-port deployer (loaded) | Lower port | Divertor cassettes | 13 | 0.1 | 0.036111 | Deploy / recover RM tools | N/A |  | N/A | N/A
| Remove the right divertor cassette | Operation | 1.412 | 127.7063 | Remove Lateral Divertor Cassette | IPD; divertor cassette handler | 1.412 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Transport removed cassette to the lower port interface | Movement | 0.036111 | 127.7424 |  |  | N/A | In-port deployer (loaded) | Divertor cassettes | Lower Port | 13 | 0.1 | 0.036111 |  | N/A |  | N/A | N/A
| Collect divertor cassette from the IPD | Logistics | 0.2126 | 128.2536 |  |  | N/A |  |  |  | N/A | N/A | N/A | Collect / store Equipment or Hardware in stillage | 0.2126 | Move overhead crane to hot cell interface; collect left div cassette CCB system; move to lower port; collect left div cassette; transport to long term store; collect new handling system; transport to lower port | 128.041 | -0.29868
| Move cassette to the transport frame | Movement | 0.027778 | 128.2814 |  |  | N/A | Overhead crane (loaded) | Lower port | RM tool storage | 2 | 0.02 | 0.027778 |  | N/A |  | N/A | N/A
| Install right cassette into the transport frame | Logistics | 0.2126 | 128.494 |  |  | N/A |  |  |  | N/A | N/A | N/A | Collect / store Equipment or Hardware in stillage | 0.2126 |  | N/A | N/A
| Move overhead crane to hot cell interface | Movement | 0.013889 | 128.5079 |  |  | N/A | Overhead crane (unloaded) | RM tool storage | Hot Cell Interface | 10 | 0.2 | 0.013889 |  | N/A |  | N/A | N/A
| Collect divertor cassette CCB system | Logistics | 0.0492 | 128.5571 |  |  | N/A |  |  |  | N/A | N/A | N/A | Store / collect RM equipment from laydown area | 0.0492 |  | N/A | N/A
| Move CCB system to the divertor cassette | Movement | 0.13889 | 128.696 |  |  | N/A | Overhead crane (loaded) | Hot Cell Interface | RM tool storage | 10 | 0.02 | 0.13889 |  | N/A |  | N/A | N/A
| Install contamination control barrier over the remoted cassette | Operation | 0.1983 | 128.8943 | Install contamination control barrier | Overhead crane; CCB system | 0.1983 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Collect divertor cassette transport frame with the overhead crane | Logistics | 0.0492 | 128.9435 |  |  | N/A |  |  |  | N/A | N/A | N/A | Store / collect RM equipment from laydown area | 0.0492 |  | N/A | N/A
| Move divertor cassette to the hot cell interface | Movement | 0.13889 | 129.0824 |  |  | N/A | Overhead crane (loaded) | RM tool storage | Hot Cell Interface | 10 | 0.02 | 0.13889 |  | N/A |  | N/A | N/A
| Deposit packaged right divertor cassette onto the hot cell interface | Logistics | 0.0492 | 129.1316 |  |  | N/A |  |  |  | N/A | N/A | N/A | Store / collect RM equipment from laydown area | 0.0492 |  | N/A | N/A
Cassette Removal Complete | End Time |  |  | 129.1316
| Operational Time |  |  | 104.5777 | F |  | 65.72%
| Logistical Time |  |  | 17.6541 | 13.67% |  | 11.09%
| Movement Time |  |  | 5.0769 | 3.932% |  | 3.19%
| Delays due to logistics |  |  | 1.8228 | 1.412% |  | 1.145%
Store divetor cassette handler and recommission the pipe module handler | Move overhead crane to the lower port | Movement | 0.018056 | 129.1496 |  |  | N/A | Overhead crane (unloaded) | Hot Cell Interface | Lower Port | 13 | 0.2 | 0.018056 | Deploy / recover RM tools | N/A |  | N/A | N/A
| Decouple the cassette handler from the IPD | Operation | 0.134 | 129.2836 | Couple / decouple IPD movers | MPR | 0.134 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Collect cassette handler with the overhead crane | Logistics | 0.0492 | 129.3328 |  |  | N/A |  |  |  | N/A | N/A | N/A | Store / collect RM equipment from laydown area | 0.0492 |  | N/A | N/A
| Move overhead crane to the RM equipment laydown area | Movement | 0.11111 | 129.444 |  |  | N/A | Overhead crane (loaded) | Lower port | RM equipment stillage | 8 | 0.02 | 0.11111 |  | N/A |  | N/A | N/A
| Store the divetor cassette handler | Logistics | 0.2126 | 129.6566 |  |  | N/A |  |  |  | N/A | N/A | N/A | Collect / store Equipment or Hardware in stillage | 0.2126 |  | N/A | N/A
| Collect the pipe module handler | Logistics | 0.2126 | 129.8692 |  |  | N/A |  |  |  | N/A | N/A | N/A | Collect / store Equipment or Hardware in stillage | 0.2126 |  | N/A | N/A
| Move overhead crane to lower port | Movement | 0.11111 | 129.9803 |  |  | N/A | Overhead crane (loaded) | RM equipment stillage | Lower Port | 8 | 0.02 | 0.11111 |  | N/A |  | N/A | N/A
| Place the pipe module handering onto the threshold rails | Logistics | 0.0492 | 130.0295 |  |  | N/A |  |  |  | N/A | N/A | N/A | Store / collect RM equipment from laydown area | 0.0492 |  | N/A | N/A
| Couple the handler to the IPD | Operation | 0.134 | 130.1635 | Couple / decouple IPD movers | MPR | 0.134 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Commission the pipe module handler | Operation | 1.332 | 131.4955 | Install and commission the IPD trailer | MPR; IPD | 1.332 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Collect MPC actuation tooling from tool storage | Logistics | 0.0492 | 131.5447 |  |  | N/A |  |  |  | N/A | N/A | N/A | Store / collect RM equipment from laydown area | 0.0492 |  | N/A | N/A
| Transfer MPC actiation tooling to the IPD | Logistics | 0.0492 | 131.5939 |  |  | N/A |  |  |  | N/A | N/A | N/A | Store / collect RM equipment from laydown area | 0.0492 |  | N/A | N/A
Remove Outboard blanket pipework | Move the IPD to the pipe module | Movement | 0.0055556 | 131.5994 |  |  | N/A | In-port deployer (loaded) | Vacuum pumping equipment | Divertor pipe modules | 2 | 0.1 | 0.0055556 |  | N/A |  | N/A | N/A
| Position the pipe module handler onto the pipe module | Logistics | 0.38 | 131.9794 |  |  | N/A |  |  |  | N/A | N/A | N/A | Reposition tool within Port | 0.38 |  | N/A | N/A
| Install MPC actuation tooling | Operation | 0.3056 | 132.285 | Install Mechanical pipe connection tooling | MPC tooling | 0.3056 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Remove pipe module access cover | Operation | 2.01 | 134.295 | Remove divertor pipe module access cover | Dexterous robot arm | 2.01 |  |  |  | N/A | N/A | N/A | Recover Tool / Hardware from the Port | N/A |  | N/A | N/A
| Store removed access cover | Logistics | 0.0492 | 134.3442 |  |  | N/A |  |  |  | N/A | N/A | N/A | Store / collect RM equipment from laydown area | 0.0492 |  | N/A | N/A
| Collect pipe inspection tooling | Logistics | 0.362 | 134.7062 |  |  | N/A |  |  |  | N/A | N/A | N/A | Deploy / recover RM tools | 0.362 |  | N/A | N/A
| Inspect outboard blanket pipework | Operation | 1.58 | 136.2862 | Inspect outboard blanket pipe in-bore and pipe module interface | dexterous robot arm | 1.58 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Collect SJS deployment system from the storage location | Logistics | 0.6 | 136.8862 |  |  | N/A |  |  |  | N/A | N/A | N/A | Recover Tool / Hardware from the Port | 0.6 |  | N/A | N/A
| Release blanket pipe module mechanical pipe connection | Operation | 0.1202 | 137.0064 | Actuate MPC tooling | Dexterous robot arm | 0.1202 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Disconnect outboard blanket pipe module from the divertor cassette | Operation | 0.82284 | 137.8293 | Disconnect outboard blanket pipe module | Outboard pipe module handler; SJS cutting system | 0.82284 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Replace SJS into storage location | Logistics | 0.362 | 138.1913 |  |  | N/A |  |  |  | N/A | N/A | N/A | Deploy / recover RM tools | 0.362 |  | N/A | N/A
| Reposition high layload arm to support the divertor pipe module | Logistics | 0.38 | 138.5713 |  |  | N/A |  |  |  | N/A | N/A | N/A | Reposition tool within Port | 0.38 |  | N/A | N/A
| Engage pipe module handling fixations | Logistics | 0.2126 | 138.7839 |  |  | N/A |  |  |  | N/A | N/A | N/A | Collect / store Equipment or Hardware in stillage | 0.2126 |  | N/A | N/A
| Reposition dexterous robot arm to release pipe module fixations | Logistics | 0.38 | 139.1639 |  |  | N/A |  |  |  | N/A | N/A | N/A | Reposition tool within Port | 0.38 |  | N/A | N/A
| Release outboard blanket pipe module fixations | Operation | 0.118 | 139.2819 | Release lower port pipe module from the port fixations | Outboard pipe module handler | 0.118 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Remove the outboard blanket pipe module from the port, using the IPD | Operation | 3 | 142.2819 | Remove pipe module from the port | Outboard pipe module handler; IPD | 3 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Collect the outboard blanket pipe module using the overhead crane | Operation | 0.0243 | 142.3062 | Actuate handling interfaces | Outboard pipe module handler; Overhead crane | 0.0243 |  |  |  | N/A | N/A | N/A | Store / collect RM equipment from laydown area | N/A |  | N/A | N/A
| Release the outboard blanket pipe module from the robot arm | Operation | 0.0243 | 142.3305 | Actuate handling interfaces | Outboard pipe module handler; Overhead crane | 0.0243 |  |  |  | N/A | N/A | N/A | Store / collect RM equipment from laydown area | N/A |  | N/A | N/A
| Move overhead crane from lower port to the hot cell interface | Movement | 0.18056 | 142.511 |  |  | N/A | Overhead crane (loaded) | Lower port | Hot Cell Interface | 13 | 0.02 | 0.18056 |  | N/A | Collect right divetor cassette; store in long term PP store; collect outboard blanket pipe module; transfer into the port | 130.3657 | 11.9647
| Place outboard blanket pipe module into the transport cask | Logistics | 0.2126 | 142.7236 |  |  | N/A |  |  |  | N/A | N/A | N/A | Collect / store Equipment or Hardware in stillage | 0.2126 |  | N/A | N/A
Store pipe module handler and disconnect the inboard pipe modulecommission inboard pipe module handler | Move crane to lower port | Movement | 0.018056 | 142.7417 |  |  | N/A | Overhead crane (unloaded) | Hot Cell Interface | Lower Port | 13 | 0.2 | 0.018056 |  | N/A |  | N/A | N/A
| Decouple the pipe module handler from IPD | Operation | 0.134 | 142.8757 | Couple / decouple IPD movers | MPR | 0.134 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Collect handler with the overhead crane | Logistics | 0.0492 | 142.9249 |  |  | N/A |  |  |  | N/A | N/A | N/A | Store / collect RM equipment from laydown area | 0.0492 |  | N/A | N/A
| Deploy IPD to the inboard blanket access point | Movement | 0.022222 | 142.9471 |  |  | N/A | In-port deployer (loaded) | Lower port | Divertor pipe modules | 8 | 0.1 | 0.022222 |  | N/A |  | N/A | N/A
| Open the inboard blanket pipe module | Operation | 8.04 | 150.9871 | Remove inboard blanket pipe module access cover | IPD; dexterous robot arm | 8.04 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Collect tehe SJS storage system from the in-port storage location | Logistics | 0.0492 | 151.0363 |  |  | N/A |  |  |  | N/A | N/A | N/A | Store / collect RM equipment from laydown area | 0.0492 |  | N/A | N/A
| Move IPD to the upper location | Movement | 0.013889 | 151.0502 |  |  | N/A | In-port deployer (loaded) | Divertor pipe modules | Divertor cassettes | 5 | 0.1 | 0.013889 |  | N/A |  | N/A | N/A
| Cut inboard pipe module welded pipe joints using the SJS | Operation | 0.54393 | 151.5941 | Disconnect inboard blanket pipe module | inboard pipe module handler; SJS cutting system | 0.54393 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Remove the IPD system from the port, with the SJS deployment system | Movement | 0.036111 | 151.6302 |  |  | N/A | In-port deployer (loaded) | Divertor cassettes | Lower Port | 13 | 0.1 | 0.036111 |  | N/A |  | N/A | N/A
| Store the SJS deployment system on the SJS cask | Logistics | 0.0492 | 151.6794 |  |  | N/A |  |  |  | N/A | N/A | N/A | Store / collect RM equipment from laydown area | 0.0492 |  | N/A | N/A
| Move overhead crane to the hot cell interface | Movement | 0.0083333 | 151.6878 |  |  | N/A | Overhead crane (unloaded) | RM equipment stillage | Hot Cell Interface | 6 | 0.2 | 0.0083333 |  | N/A |  | N/A | N/A
| Collect inboard pipe module handling equipment | Logistics | 0.0492 | 151.737 |  |  | N/A |  |  |  | N/A | N/A | N/A | Store / collect RM equipment from laydown area | 0.0492 | Transfer thre pipe module out of the hot cell and store; collect inboard pipe module handler from stores; Transfer into hot cell | 143.7378 | 7.95
| Move to the lower port interface | Movement | 0.18056 | 151.9175 |  |  | N/A | Overhead crane (loaded) | Hot Cell Interface | Lower Port | 13 | 0.02 | 0.18056 |  | N/A |  | N/A | N/A
| Install inboard pipe module handler on the threshold rails | Logistics | 0.0492 | 151.9667 |  |  | N/A |  |  |  | N/A | N/A | N/A | Store / collect RM equipment from laydown area | 0.0492 |  | N/A | N/A
| Commission the IPD system | Operation | 1.332 | 153.2987 | Install and commission the IPD trailer | MPR; IPD | 1.332 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
Remove Inboard blanket pipework | Move the IPD to the inboard pipe module location | Movement | 0.022222 | 153.3209 |  |  | N/A | In-port deployer (loaded) | Lower port | Divertor pipe modules | 8 | 0.1 | 0.022222 |  | N/A |  | N/A | N/A
| Deploy forward pipe module handling interface | Logistics | 0.38 | 153.7009 |  |  | N/A |  |  |  | N/A | N/A | N/A | Reposition tool within Port | 0.38 |  | N/A | N/A
| Release the IPD tractor from the pipe module handler | Logistics | 0.0492 | 153.7501 |  |  | N/A |  |  |  | N/A | N/A | N/A | Store / collect RM equipment from laydown area | 0.0492 |  | N/A | N/A
| Move the IPD tractor to the rear pipe module handling interface | Movement | 0.013889 | 153.764 |  |  | N/A | In-port deployer (loaded) | Divertor pipe modules | Divertor cassettes | 5 | 0.1 | 0.013889 |  | N/A |  | N/A | N/A
| Collect rear handling interface | Logistics | 0.0492 | 153.8132 |  |  | N/A |  |  |  | N/A | N/A | N/A | Store / collect RM equipment from laydown area | 0.0492 |  | N/A | N/A
| Install rear handling interface | Logistics | 0.0492 | 153.8624 |  |  | N/A |  |  |  | N/A | N/A | N/A | Store / collect RM equipment from laydown area | 0.0492 |  | N/A | N/A
| Release pipe module fixations | Operation | 0.22 | 154.0824 | Release / install inboard blanket on VV fixations | Dexterous Robot arm | 0.22 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| IPD tractor returns to the transport configuration | Movement | 0.013889 | 154.0963 |  |  | N/A | In-port deployer (loaded) | Divertor cassettes | Divertor pipe modules | 5 | 0.1 | 0.013889 |  | N/A |  | N/A | N/A
| Collect long reach tooling from the IPD | Logistics | 0.0492 | 154.1455 |  |  | N/A |  |  |  | N/A | N/A | N/A | Store / collect RM equipment from laydown area | 0.0492 |  | N/A | N/A
| Release mechanical pipe connection alignment fixations | Operation | 0.22 | 154.3655 | Release / install inboard blanket on VV fixations | Inboard pipe module handler | 0.22 |  |  |  | N/A | N/A | N/A | Store / collect RM equipment from laydown area | N/A |  | N/A | N/A
| Lift the inboard blanket module from the VV | Operation | 0.118 | 154.4835 | Release lower port pipe module from the port fixations | Dexterous robot arm | 0.118 |  |  |  | N/A | N/A | N/A | Deploy / recover RM tools | N/A |  | N/A | N/A
| Remove the pipe module from the port | Operation | 3 | 157.4835 | Remove pipe module from the port | Inboard pipe module handler; IPD | 3 | In-port deployer (loaded) | Divertor cassettes | Lower Port | 13 | 0.1 | N/A |  | N/A |  | N/A | N/A
| Lower the pipe module to rest on the threshold rails | Logistics | 0.0492 | 157.5327 |  |  | N/A |  |  |  | N/A | N/A | N/A | Store / collect RM equipment from laydown area | 0.0492 |  | N/A | N/A
| Using the MPR, release the froward pipe module fixation | Operation | 0.0243 | 157.557 | Actuate handling interfaces | MPR | 0.0243 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Move the MPR to the rear pipe module fixation | Movement | 0.00066934 | 157.5577 |  |  | N/A | Multi-purpose robot (transport) | RM tool storage | Lower Port | 2 | 0.83 | 0.00066934 |  | N/A |  | N/A | N/A
| Release the inboard pipe module hander from the IPD system | Operation | 0.0243 | 157.582 | Actuate handling interfaces | MPR | 0.0243 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Collect the pipe module handler using the overhead crane | Logistics | 0.0492 | 157.6312 |  |  | N/A |  |  |  | N/A | N/A | N/A | Store / collect RM equipment from laydown area | 0.0492 |  | N/A | N/A
| Move the pipe module handler to the RM equipment stillage | Movement | 0.11111 | 157.7423 |  |  | N/A | Overhead crane (loaded) | Lower port | RM equipment stillage | 8 | 0.02 | 0.11111 |  | N/A |  | N/A | N/A
| Release the pipe module handler for short term storage | Logistics | 0.0492 | 157.7915 |  |  | N/A |  |  |  | N/A | N/A | N/A | Store / collect RM equipment from laydown area | 0.0492 |  | N/A | N/A
| Move the overehead crane to the lower port | Movement | 0.011111 | 157.8026 |  |  | N/A | Overhead crane (unloaded) | RM equipment stillage | Lower Port | 8 | 0.2 | 0.011111 |  | N/A |  | N/A | N/A
| Collect the inboard pipe module from the threshold rails | Logistics | 0.0492 | 157.8518 |  |  | N/A |  |  |  | N/A | N/A | N/A | Store / collect RM equipment from laydown area | 0.0492 |  | N/A | N/A
| Move the pipe module to the hot cell interface | Movement | 0.18056 | 158.0324 |  |  | N/A | Overhead crane (loaded) | Lower port | Hot Cell Interface | 13 | 0.02 | 0.18056 |  | N/A | Collect packaged outboard pipe module; store in long term PP store; collect inboard blanket pipe cask; transfer into the port | 130.3657 | 27.4861
| Install the removed pipe module into a transport cask | Logistics | 0.2126 | 158.245 |  |  | N/A |  |  |  | N/A | N/A | N/A | Collect / store Equipment or Hardware in stillage | 0.2126 |  | N/A | N/A
| Seal cask's contamination control barrier | Operation | 0.1983 | 158.4433 | Install contamination control barrier | CCB System | 0.1983 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Transfer the transport cask out of the hot cell | Logistics | 0.22 | 158.6633 |  |  | N/A |  |  |  | N/A | N/A | N/A | Collect / desposit hardware from the hot cell interface | 0.22 |  | N/A | N/A
Inspection revealed in-port area | Deploy the IPD tractor into the port | Movement | 0.022222 | 158.6855 |  |  | N/A | In-port deployer (loaded) | Lower Port | Divertor pipe modules | 8 | 0.1 | 0.022222 |  | N/A | Collect in-port inspection system from RM tool storage; move to lower port; install and commission on IPD | 158.0598 | 0.60346
| Inspect revealed port liner | Operation | 0.36361 | 159.0491 | Inspect revealed area of the lower port | Long reach robot arm | 0.36361 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Remove inspection system from the port | Movement | 0.036111 | 159.0852 |  |  | N/A | In-port deployer (loaded) | Vacuum pumping equipment | RM tool storage | 13 | 0.1 | 0.036111 |  | N/A |  | N/A | N/A
| Return inspection tooling to RM storage | Logistics | 0.0492 | 159.1344 |  |  | N/A |  |  |  | N/A | N/A | N/A | Store / collect RM equipment from laydown area | 0.0492 |  | N/A | N/A
Hardware Removal Complete | End Time |  |  | 159.1344
| Operational Time |  |  | 128.4014 | 80.69%
| Logistical Time |  |  | 22.7159 | 14.27%
| Movement Time |  |  | 6.1943 | 3.892%
| Delays due to logistics |  |  | 1.8228 | 1.145%
Collect replacement pipe module and commission inboard pipe module handler | Cassette Installation Required | Operation | 0 | 0 | Cassette Installation Required |  | 0 |  |  |  | N/A | N/A | N/A | Deploy / recover RM tools | N/A |  | N/A | N/A
| Move overhead crane to the hot cell interface | Movement | 0.18056 | 0.18056 |  |  | N/A | Overhead crane (loaded) | Lower port | Hot Cell Interface | 13 | 0.02 | 0.18056 | Deploy / recover RM tools | N/A |  | N/A | N/A
| Collect the replacement inboard blanket pipe module from hot cell interface | Logistics | 0.2126 | 0.8966 |  |  | N/A |  |  |  | N/A | N/A | N/A | Collect / store Equipment or Hardware in stillage | 0.2126 | Move ex-vessel transporter to PP hardware store; collect replacement inboard blanket pipe module from stores; transfer into the hot cell | 0.684 | -0.50345
| Transport to the lower port interface | Movement | 0.18056 | 1.0772 |  |  | N/A | Overhead crane (loaded) | Hot Cell Interface | Lower Port | 13 | 0.02 | 0.18056 |  | N/A |  | N/A | N/A
| Place pipe module onto the threshold rails | Logistics | 0.336 | 1.4132 |  |  | N/A |  |  |  | N/A | N/A | N/A | Store / collect items with the overhead crane | 0.336 |  | N/A | N/A
| Move overhead crane to RM equipment storage | Movement | 0.011111 | 1.4243 |  |  | N/A | Overhead crane (unloaded) | Lower Port | RM equipment stillage | 8 | 0.2 | 0.011111 | Deploy / recover RM tools | N/A |  | N/A | N/A
| Collect inboard pipe module handling equipment | Logistics | 0.336 | 1.7603 |  |  | N/A |  |  |  | N/A | N/A | N/A | Store / collect items with the overhead crane | 0.336 |  | N/A | N/A
| Move pipe module handler to the lower port | Movement | 0.11111 | 1.8714 |  |  | N/A | Overhead crane (loaded) | RM equipment stillage | Lower Port | 8 | 0.02 | 0.11111 |  | N/A |  | N/A | N/A
| Install pipe module handler onto the port rails | Logistics | 0.336 | 2.2074 |  |  | N/A |  |  |  | N/A | N/A | N/A | Store / collect items with the overhead crane | 0.336 |  | N/A | N/A
| Couple the pipe module handler to the IPD tractor | Operation | 0.134 | 2.3414 | Couple / decouple IPD movers | MPR | 0.134 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Commission the IPD control system | Operation | 1.332 | 3.6734 | Install and commission the IPD trailer | MPR; IPD | 1.332 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
Install Inboard Blanket Pipe Module | Move the pipe module to it's installed location | Movement | 0.022222 | 3.6956 |  |  | N/A | In-port deployer (loaded) | Lower port | Divertor pipe modules | 8 | 0.1 | 0.022222 | Deploy / recover RM tools | N/A |  | N/A | N/A
| Place pipe module into final installed positions | Logistics | 0.0492 | 3.7448 |  |  | N/A |  |  |  | N/A | N/A | N/A | Store / collect RM equipment from laydown area | 0.0492 |  | N/A | N/A
| Collect long reach tooling from the IPD | Logistics | 0.0492 | 3.794 |  |  | N/A |  |  |  | N/A | N/A | N/A | Store / collect RM equipment from laydown area | 0.0492 |  | N/A | N/A
| Actuate pipe module MPC fixations | Operation | 0.22 | 4.014 | Release / install inboard blanket on VV fixations | Inboard pipe module handler | 0.22 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Release the lower end of the pipe module from the handler | Operation | 0.0243 | 4.0383 | Actuate handling interfaces | Inboard pipe module handler | 0.0243 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Move the IPD tractor to the rear pipe module handling interface | Movement | 0.013889 | 4.0522 |  |  | N/A | In-port deployer (loaded) | Divertor pipe modules | Divertor cassettes | 5 | 0.1 | 0.013889 |  | N/A |  | N/A | N/A
| Actuate the pipe module fixations | Operation | 0.22 | 4.2722 | Release / install inboard blanket on VV fixations | Inboard pipe module handler | 0.22 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Return IPD to lower location | Movement | 0.013889 | 4.2861 |  |  | N/A | In-port deployer (loaded) | Divertor cassettes | Divertor pipe modules | 5 | 0.1 | 0.013889 |  | N/A |  | N/A | N/A
| Release forward handling interface | Operation | 0.0243 | 4.3104 | Actuate handling interfaces |  | 0.0243 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Remove the IPD tractor and trailer from the port | Movement | 0.022222 | 4.3326 |  |  | N/A | In-port deployer (loaded) | Divertor pipe modules | Lower Port | 8 | 0.1 | 0.022222 |  | N/A |  | N/A | N/A
| Release the pipe module handler from the IPD | Operation | 0.134 | 4.4666 | Couple / decouple IPD movers | MPR | 0.134 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Collect pipe module handler from the IPD | Logistics | 0.336 | 4.8026 |  |  | N/A |  |  |  | N/A | N/A | N/A | Store / collect items with the overhead crane | 0.336 |  | N/A | N/A
| Move to hot cell interface | Movement | 0.18056 | 4.9832 |  |  | N/A | Overhead crane (loaded) | Lower port | Hot Cell Interface | 13 | 0.02 | 0.18056 |  | N/A |  | N/A | N/A
| Transfer the IB pipe module handler to the hot cell interface | Logistics | 0.336 | 5.3192 |  |  | N/A |  |  |  | N/A | N/A | N/A | Store / collect items with the overhead crane | 0.336 |  | N/A | N/A
Collect and commission SJS tooling | Move overhead crane over to RM equipment storage | Movement | 0.0083333 | 5.3275 |  |  | N/A | Overhead crane (unloaded) | Hot Cell Interface | RM equipment stillage | 6 | 0.2 | 0.0083333 |  | N/A |  | N/A | N/A
| Collect IPD trailerq | Logistics | 0.336 | 5.6635 |  |  | N/A |  |  |  | N/A | N/A | N/A | Store / collect items with the overhead crane | 0.336 |  | N/A | N/A
| Move to threshold rails | Movement | 0.11111 | 5.7746 |  |  | N/A | Overhead crane (loaded) | RM equipment stillage | Lower Port | 8 | 0.02 | 0.11111 |  | N/A |  | N/A | N/A
| Place trailer onto the treshold rails | Logistics | 0.336 | 6.1106 |  |  | N/A |  |  |  | N/A | N/A | N/A | Store / collect items with the overhead crane | 0.336 |  | N/A | N/A
| Couple the trailer to the IPD | Operation | 0.134 | 6.2446 | Couple / decouple IPD movers | MPR | 0.134 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Commission the trailer control system | Operation | 1.332 | 7.5766 | Install and commission the IPD trailer | MPR; IPD | 1.332 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Move MPR to the SJS service cask | Movement | 0.0026774 | 7.5793 |  |  | N/A | Multi-purpose robot (transport) | RM equipment stillage | Lower Port | 8 | 0.83 | 0.0026774 |  | N/A |  | N/A | N/A
| Collect the SJS deployment system | Logistics | 0.0492 | 7.6285 |  |  | N/A |  |  |  | N/A | N/A | N/A | Store / collect RM equipment from laydown area | 0.0492 |  | N/A | N/A
| Transfer the SJS deployment system to the IPD robot arm | Logistics | 0.0492 | 7.6777 |  |  | N/A |  |  |  | N/A | N/A | N/A | Store / collect RM equipment from laydown area | 0.0492 |  | N/A | N/A
| Move IPD tractor to the port mouth | Movement | 0.0083333 | 7.686 |  |  | N/A | In-port deployer (loaded) | Lower port | Vacuum pumping equipment | 3 | 0.1 | 0.0083333 |  | N/A |  | N/A | N/A
| Install SJS umbilible into the SJS pulley | Operation | 0.516 | 8.202 | Install SJS pulley system | Long reach robot arm | 0.516 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
Connect inboard blanket pipe module to services | Deploy the IPD tractor to the inboard pipe modules | Movement | 0.019444 | 8.2215 |  |  | N/A | In-port deployer (loaded) | Vacuum pumping equipment | Divertor cassettes | 7 | 0.1 | 0.019444 |  | N/A |  | N/A | N/A
| Weld inboard pipe joints | Operation | 8.2972 | 16.5186 | Connect Lower Pork Outboard Blanket Pipe Module | SJS welding system | 8.2972 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Store SJS deployment system onto port storage location | Logistics | 0.0492 | 16.5678 |  |  | N/A |  |  |  | N/A | N/A | N/A | Store / collect RM equipment from laydown area | 0.0492 |  | N/A | N/A
| Collect pipe module inspection tooling | Logistics | 0.0492 | 16.617 |  |  | N/A |  |  |  | N/A | N/A | N/A | Store / collect RM equipment from laydown area | 0.0492 |  | N/A | N/A
| Inspect inboard pipe module access port | Operation | 1.048 | 17.665 | Inspect inboard blanket pipe in-bore and pipe module interface | Dexterous robot arm | 1.048 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Store inspection tooling | Logistics | 0.0492 | 17.7142 |  |  | N/A |  |  |  | N/A | N/A | N/A | Store / collect RM equipment from laydown area | 0.0492 |  | N/A | N/A
| Collect pipe module access lid | Logistics | 0.0492 | 17.7634 |  |  | N/A |  |  |  | N/A | N/A | N/A | Store / collect RM equipment from laydown area | 0.0492 |  | N/A | N/A
| Install access port cover | Operation | 8.94 | 26.7034 | Install inboard blanket pipe module access cover | Dexterous Robot arm | 8.94 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Store fixation tooling | Logistics | 0.0492 | 26.7526 |  |  | N/A |  |  |  | N/A | N/A | N/A | Store / collect RM equipment from laydown area | 0.0492 |  | N/A | N/A
| Move arm to the MPC location | Logistics | 0.38 | 27.1326 |  |  | N/A |  |  |  | N/A | N/A | N/A | Reposition tool within Port | 0.38 |  | N/A | N/A
| Remove the MPC tooling from the pipe module | Operation | 0.1233 | 27.2559 | Remove MPC tooling | Dexterous robot arm | 0.1233 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Store on the IPD | Logistics | 0.0492 | 27.3051 |  |  | N/A |  |  |  | N/A | N/A | N/A | Store / collect RM equipment from laydown area | 0.0492 |  | N/A | N/A
| Collect SJS deployment system from the port storage location | Logistics | 0.0492 | 27.3543 |  |  | N/A |  |  |  | N/A | N/A | N/A | Store / collect RM equipment from laydown area | 0.0492 |  | N/A | N/A
| Move IPD to the lower pipe module locations | Movement | 0.013889 | 27.3682 |  |  | N/A | In-port deployer (loaded) | Divertor cassettes | Divertor pipe modules | 5 | 0.1 | 0.013889 |  | N/A |  | N/A | N/A
| Store SJS in horizontal port storage location | Logistics | 0.0492 | 27.4174 |  |  | N/A |  |  |  | N/A | N/A | N/A | Store / collect RM equipment from laydown area | 0.0492 |  | N/A | N/A
| Remove the IPD from the port | Movement | 0.022222 | 27.4396 |  |  | N/A | In-port deployer (loaded) | Divertor pipe modules | Lower Port | 8 | 0.1 | 0.022222 |  | N/A |  | N/A | N/A
Collect and commission the outboard pipe module handler | Move overhead crane over to RM equipment storage | Movement | 0.0083333 | 27.448 |  |  | N/A | Overhead crane (unloaded) | Hot Cell Interface | RM equipment stillage | 6 | 0.2 | 0.0083333 |  | N/A |  | N/A | N/A
| Collect outboard pipe module handler | Logistics | 0.336 | 27.784 |  |  | N/A |  |  |  | N/A | N/A | N/A | Store / collect items with the overhead crane | 0.336 |  | N/A | N/A
| Move to threshold rails | Movement | 0.11111 | 27.8951 |  |  | N/A | Overhead crane (loaded) | RM equipment stillage | Lower Port | 8 | 0.02 | 0.11111 |  | N/A |  | N/A | N/A
| Place trailer onto the treshold rails | Logistics | 0.336 | 28.2311 |  |  | N/A |  |  |  | N/A | N/A | N/A | Store / collect items with the overhead crane | 0.336 |  | N/A | N/A
| Couple the trailer to the IPD | Operation | 0.134 | 28.3651 | Couple / decouple IPD movers | MPR | 0.134 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Commission the trailer control system | Operation | 1.332 | 29.6971 | Install and commission the IPD trailer | MPR; IPD | 1.332 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Move overhead crane to hot cell interface | Movement | 0.018056 | 29.7151 |  |  | N/A | Overhead crane (unloaded) | Lower port | Hot Cell Interface | 13 | 0.2 | 0.018056 |  | N/A | Return empty transport stillage to PP stores; collect new outboard blanket pipe module; transport into lower port hot cell | 1.9969 | 27.7002
| Collect the outboard blanket pipe module from the port interface | Logistics | 0.336 | 30.0511 |  |  | N/A |  |  |  | N/A | N/A | N/A | Store / collect items with the overhead crane | 0.336 |  | N/A | N/A
| Transfer outboard blanket pipe module to the lower port | Movement | 0.18056 | 30.2317 |  |  | N/A | Overhead crane (loaded) | Hot Cell Interface | Lower Port | 13 | 0.02 | 0.18056 |  | N/A |  | N/A | N/A
| Engage robot arm with pipe module | Logistics | 0.38 | 30.6117 |  |  | N/A |  |  |  | N/A | N/A | N/A | Reposition tool within Port | 0.38 |  | N/A | N/A
| Transfer the pipe module from the crane to the pipe module handler | Operation | 0.0243 | 30.636 | Actuate handling interfaces | overhead crane; Outboard pipe module handler | 0.0243 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Release the pipe module from the overhead crane | Operation | 0.0243 | 30.6603 | Actuate handling interfaces | overhead crane; Outboard pipe module handler | 0.0243 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
Connect Ouboard blanket pipe module to services | Deploy the IPD tractor to the outboard blanket pipe module location | Movement | 0.022222 | 30.6825 |  |  | N/A | In-port deployer (loaded) | Lower port | Divertor pipe modules | 8 | 0.1 | 0.022222 |  | N/A |  | N/A | N/A
| Collect MPC tooling from IPD | Logistics | 0.0492 | 30.7317 |  |  | N/A |  |  |  | N/A | N/A | N/A | Store / collect RM equipment from laydown area | 0.0492 |  | N/A | N/A
| Install MPC tooling onto the port pipework | Operation | 0.3056 | 31.0373 | Install Mechanical pipe connection tooling | Dexterous robot arm | 0.3056 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Actuate the MPC tooling | Operation | 0.1202 | 31.1575 | Actuate MPC tooling | MPC tooling | 0.1202 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Remove the MPC seal plug | Operation | 0.0403 | 31.1978 | Install / remove MPC seals | Dexterous robot arm | 0.0403 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Store MPC seal on the IPD | Logistics | 0.0492 | 31.247 |  |  | N/A |  |  |  | N/A | N/A | N/A | Store / collect RM equipment from laydown area | 0.0492 |  | N/A | N/A
| Place pipe module into installed position | Logistics | 0.2126 | 31.4596 |  |  | N/A |  |  |  | N/A | N/A | N/A | Collect / store Equipment or Hardware in stillage | 0.2126 |  | N/A | N/A
| Actuate the MPC tooling to align pipe module | Operation | 0.1202 | 31.5798 | Actuate MPC tooling | MPC tooling | 0.1202 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Weld inboard pipe joints | Operation | 5.5314 | 37.1112 | Connect Lower Pork Inboard Blanket Pipe Module | outboard pipe module handler; SJS welding system | 5.5314 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Store SJS deployment system onto port storage location | Logistics | 0.0492 | 37.1604 |  |  | N/A |  |  |  | N/A | N/A | N/A | Store / collect RM equipment from laydown area | 0.0492 |  | N/A | N/A
| Collect pipe module inspection tooling | Logistics | 0.0492 | 37.2096 |  |  | N/A |  |  |  | N/A | N/A | N/A | Store / collect RM equipment from laydown area | 0.0492 |  | N/A | N/A
| Inspect inboard pipe module access port | Operation | 1.048 | 38.2576 | Inspect inboard blanket pipe in-bore and pipe module interface | Dexterous robot arm | 1.048 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Store inspection tooling | Logistics | 0.0492 | 38.3068 |  |  | N/A |  |  |  | N/A | N/A | N/A | Store / collect RM equipment from laydown area | 0.0492 |  | N/A | N/A
| Collect pipe module access lid | Logistics | 0.0492 | 38.356 |  |  | N/A |  |  |  | N/A | N/A | N/A | Store / collect RM equipment from laydown area | 0.0492 |  | N/A | N/A
| Install access port cover | Operation | 8.94 | 47.296 | Install inboard blanket pipe module access cover | Dexterous robot arm | 8.94 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Store fixation tooling | Logistics | 0.0492 | 47.3452 |  |  | N/A |  |  |  | N/A | N/A | N/A | Store / collect RM equipment from laydown area | 0.0492 |  | N/A | N/A
| Move arm to the MPC location | Logistics | 0.38 | 47.7252 |  |  | N/A |  |  |  | N/A | N/A | N/A | Reposition tool within Port | 0.38 |  | N/A | N/A
| Remove the MPC tooling from the pipe module | Operation | 0.1233 | 47.8485 | Remove MPC tooling | Dexterous robot arm | 0.1233 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Store on the IPD | Logistics | 0.0492 | 47.8977 |  |  | N/A |  |  |  | N/A | N/A | N/A | Store / collect RM equipment from laydown area | 0.0492 |  | N/A | N/A
| Collect SJS deployment system from the port storage location | Logistics | 0.0492 | 47.9469 |  |  | N/A |  |  |  | N/A | N/A | N/A | Store / collect RM equipment from laydown area | 0.0492 |  | N/A | N/A
| Move IPD to the lower pipe module locations | Movement | 0.013889 | 47.9608 |  |  | N/A | In-port deployer (loaded) | Divertor cassettes | Divertor pipe modules | 5 | 0.1 | 0.013889 |  | N/A |  | N/A | N/A
| Store SJS in horizontal port storage location | Logistics | 0.0492 | 48.01 |  |  | N/A |  |  |  | N/A | N/A | N/A | Store / collect RM equipment from laydown area | 0.0492 |  | N/A | N/A
| Remove the IPD from the port | Movement | 0.022222 | 48.0322 |  |  | N/A | In-port deployer (loaded) | Divertor pipe modules | Lower Port | 8 | 0.1 | 0.022222 |  | N/A |  | N/A | N/A
Store pipe module handler and commission divetor cassette handler | Move crane to lower port | Movement | 0.018056 | 48.0503 |  |  | N/A | Overhead crane (unloaded) | Hot Cell Interface | Lower Port | 13 | 0.2 | 0.018056 |  | N/A |  | N/A | N/A
| Decouple the outboard pipe module handler from IPD | Operation | 0.134 | 48.1843 | Couple / decouple IPD movers | MPR | 0.134 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Collect handler with the overhead crane | Logistics | 0.336 | 48.5203 |  |  | N/A |  |  |  | N/A | N/A | N/A | Store / collect items with the overhead crane | 0.336 |  | N/A | N/A
| Transport handler to suitable laydown location | Movement | 0.11111 | 48.6314 |  |  | N/A | Overhead crane (loaded) | Lower port | RM equipment stillage | 8 | 0.02 | 0.11111 |  | N/A |  | N/A | N/A
| Store pipe module handler | Logistics | 0.336 | 48.9674 |  |  | N/A |  |  |  | N/A | N/A | N/A | Store / collect items with the overhead crane | 0.336 |  | N/A | N/A
| Collect divertor cassette handling system | Logistics | 0.336 | 49.3034 |  |  | N/A |  |  |  | N/A | N/A | N/A | Store / collect items with the overhead crane | 0.336 |  | N/A | N/A
| Move overhead crane to the threshold rails | Movement | 0.11111 | 49.4145 |  |  | N/A | Overhead crane (loaded) | RM equipment stillage | Lower Port | 8 | 0.02 | 0.11111 |  | N/A |  | N/A | N/A
| Place divertor cassette handler onto the threshold rails | Logistics | 0.336 | 49.7505 |  |  | N/A |  |  |  | N/A | N/A | N/A | Store / collect items with the overhead crane | 0.336 |  | N/A | N/A
| Couple the divertor cassette handler to the IPD | Operation | 0.134 | 49.8845 | Couple / decouple IPD movers | MPR | 0.134 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Commission the divertor cassette handler | Operation | 1.332 | 51.2165 | Install and commission the IPD trailer | MPR; IPD | 1.332 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
Blanket Pipework Installation Complete | End Time |  |  | 51.2165
| Operational Time |  |  | 40.2227 | 25.28%
| Logistical Time |  |  | 6.0076 | 3.775%
| Movement Time |  |  | 1.2985 | 2.535%
Collect new Right Divertor cassette | Move overhead crane to the hot cell interface | Movement | 0.018056 | 51.2346 |  |  | N/A | Overhead crane (unloaded) | Lower port | Hot Cell Interface | 13 | 0.2 | 0.018056 |  | N/A | Return empty transport stillage to PP stores; collect new right divetor cassette from stores; transport into lower port hot cell | 31.1514 | 20.0651
| Collect new right divertor cassette from the transport stillage | Logistics | 0.2126 | 51.4472 |  |  | N/A |  |  |  | N/A | N/A | N/A | Collect / store Equipment or Hardware in stillage | 0.2126 |  | N/A | N/A
| Transport right divertor cassette to the lower port | Movement | 0.18056 | 51.6277 |  |  | N/A | Overhead crane (loaded) | Hot Cell Interface | Lower Port | 13 | 0.02 | 0.18056 |  | N/A |  | N/A | N/A
| Transfer the divertor cassette from the overhead crane to the cassette handler | Operation | 0.0243 | 51.652 | Actuate handling interfaces | Overhead crane; divertor cassette handler | 0.0243 |  |  |  | N/A | N/A | N/A | Store / collect RM equipment from laydown area | N/A |  | N/A | N/A
Install Right divertor cassettes | Move IPD to the inclinded port | Movement | 0.036111 | 51.6881 |  |  | N/A | In-port deployer (loaded) | Lower port | Divertor cassettes | 13 | 0.1 | 0.036111 |  | N/A |  | N/A | N/A
| Install right divertor cassette in final location | Operation | 1.486 | 53.1741 | Install Lateral Divertor Cassette | Divertor cassette handler | 1.486 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Recover IPD from the port | Movement | 0.036111 | 53.2103 |  |  | N/A | In-port deployer (loaded) | Divertor cassettes | Lower Port | 13 | 0.1 | 0.036111 |  | N/A |  | N/A | N/A
Collect new Left Divertor cassette | Move overhead crane to the hot cell interface | Movement | 0.018056 | 53.2283 |  |  | N/A | Overhead crane (unloaded) | Lower port | Hot Cell Interface | 13 | 0.2 | 0.018056 |  | N/A |  | N/A | N/A
| Collect new left divertor cassette from the transport stillage | Logistics | 0.2126 | 54.3002 |  |  | N/A |  |  |  | N/A | N/A | N/A | Collect / store Equipment or Hardware in stillage | 0.2126 | Return empty transport stillage to PP stores; collect new left divetor cassette from stores; transport into lower port hot cell | 52.5474 | -0.8593
| Transport left divertor cassette to the lower port | Movement | 0.18056 | 54.4808 |  |  | N/A | Overhead crane (loaded) | Hot Cell Interface | Lower Port | 13 | 0.02 | 0.18056 |  | N/A |  | N/A | N/A
| Transfer the divertor cassette from the overhead crane to the cassette handler | Operation | 0.0243 | 54.5051 | Actuate handling interfaces | Overhead crane; divertor cassette handler | 0.0243 |  |  |  | N/A | N/A | N/A | Store / collect RM equipment from laydown area | N/A |  | N/A | N/A
Install new divertor cassettes | Move IPD to the inclinded port | Movement | 0.036111 | 54.5412 |  |  | N/A | In-port deployer (loaded) | Lower port | Divertor cassettes | 13 | 0.1 | 0.036111 |  | N/A |  | N/A | N/A
| Install left divertor cassette in final location | Operation | 1.486 | 56.0272 | Install Lateral Divertor Cassette | Divertor cassette handler | 1.486 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Recover IPD from the port | Movement | 0.036111 | 56.0633 |  |  | N/A | In-port deployer (loaded) | Divertor cassettes | Lower Port | 13 | 0.1 | 0.036111 |  | N/A |  | N/A | N/A
Collect new Centre Divertor cassette | Move overhead crane to the hot cell interface | Movement | 0.018056 | 56.0813 |  |  | N/A | Overhead crane (unloaded) | Lower port | Hot Cell Interface | 13 | 0.2 | 0.018056 |  | N/A |  | N/A | N/A
| Collect new centre divertor cassette from the transport stillage | Logistics | 0.2126 | 57.1532 |  |  | N/A |  |  |  | N/A | N/A | N/A | Collect / store Equipment or Hardware in stillage | 0.2126 | Return empty transport stillage to PP stores; collect new centre divetor cassette from stores; transport into lower port hot cell | 55.4005 | -0.8593
| Transport centre divertor cassette to the lower port | Movement | 0.18056 | 57.3338 |  |  | N/A | Overhead crane (loaded) | Hot Cell Interface | Lower Port | 13 | 0.02 | 0.18056 |  | N/A |  | N/A | N/A
| Transfer the divertor cassette from the overhead crane to the cassette handler | Operation | 0.0243 | 57.3581 | Actuate handling interfaces | Overhead crane; divertor cassette handler | 0.0243 |  |  |  | N/A | N/A | N/A | Store / collect RM equipment from laydown area | N/A |  | N/A | N/A
Install new Centre divertor cassettes | Move IPD to the inclinded port | Movement | 0.036111 | 57.3942 |  |  | N/A | In-port deployer (loaded) | Lower port | Divertor cassettes | 13 | 0.1 | 0.036111 |  | N/A |  | N/A | N/A
| Install centre divertor cassette in final location | Operation | 1.144 | 58.5382 | Install Centre Divertor Cassette | Divertor cassette handler | 1.144 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Recover IPD from the port | Movement | 0.036111 | 58.5743 |  |  | N/A | In-port deployer (loaded) | Divertor cassettes | Lower Port | 13 | 0.1 | 0.036111 |  | N/A |  | N/A | N/A
Remove the divetor cassette handler from the hot cell, and recommission the outboard pipe module handler | Decouple the divertor cassette handler from the IPD | Operation | 0.134 | 58.7083 | Couple / decouple IPD movers | MPR | 0.134 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Collect handler with the overhead crane | Logistics | 0.336 | 59.0443 |  |  | N/A |  |  |  | N/A | N/A | N/A | Store / collect items with the overhead crane | 0.336 |  | N/A | N/A
| Transport handler to hot cell interface | Movement | 0.18056 | 59.2249 |  |  | N/A | Overhead crane (loaded) | Lower port | Hot Cell Interface | 13 | 0.02 | 0.18056 |  | N/A |  | N/A | N/A
| Transfer the divertor cassette handler to the hot cell interface | Logistics | 0.336 | 59.5609 |  |  | N/A |  |  |  | N/A | N/A | N/A | Store / collect items with the overhead crane | 0.336 | Return empty transport stillage to PP stores; return transporter to lower port hot cell to collect divertor cassette tooling | 57.7703 | 0.80401
| Move overhead crane to RM equipment laydown area | Movement | 0.0083333 | 59.5692 |  |  | N/A | Overhead crane (unloaded) | Hot Cell Interface | RM equipment stillage | 6 | 0.2 | 0.0083333 |  | N/A |  | N/A | N/A
| Collect the outboard pipe module handler | Logistics | 0.336 | 59.9052 |  |  | N/A |  |  |  | N/A | N/A | N/A | Store / collect items with the overhead crane | 0.336 |  | N/A | N/A
| Move the pipe module handler to the lower port | Movement | 0.11111 | 60.0163 |  |  | N/A | Overhead crane (loaded) | RM equipment stillage | Lower Port | 8 | 0.02 | 0.11111 |  | N/A |  | N/A | N/A
| Place the pipe module handering onto the threshold rails | Logistics | 0.336 | 60.3523 |  |  | N/A |  |  |  | N/A | N/A | N/A | Store / collect items with the overhead crane | 0.336 |  | N/A | N/A
| Couple the handler to the IPD | Operation | 0.134 | 60.4863 | Couple / decouple IPD movers | MPR | 0.134 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Commission the IPD / handler interface | Operation | 1.332 | 61.8183 | Install and commission the IPD trailer | MPR; IPD | 1.332 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
Install and connect Right divertor pipe module | Move the overhead crane to the hot cell interface | Movement | 0.018056 | 61.8364 |  |  | N/A | Overhead crane (unloaded) | Lower port | Hot Cell Interface | 13 | 0.2 | 0.018056 |  | N/A |  | N/A | N/A
| Collect the new right divertor pipe module from the transport stillage | Logistics | 0.2126 | 62.049 |  |  | N/A |  |  |  | N/A | N/A | N/A | Collect / store Equipment or Hardware in stillage | 0.2126 | Store divertor cassette tooling in RM stores; collect right divetor pipe module from stores; transport into lower port hot cell | 58.3874 | 1.1818
| Move pipe module to lower port | Movement | 0.18056 | 62.2295 |  |  | N/A | Overhead crane (loaded) | Hot Cell Interface | Lower Port | 13 | 0.02 | 0.18056 |  | N/A |  | N/A | N/A
| Transfer the pipe module from the crane to the pipe module handler | Operation | 0.0243 | 62.2538 | Actuate handling interfaces | Overhead crane; Outboard pipe module handler | 0.0243 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Release the right divertor pipe module from the overhead crane | Operation | 0.0243 | 62.2781 | Actuate handling interfaces | Overhead crane; Outboard pipe module handler | 0.0243 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Deploy the IPD tractor to the divertor cassette pipe module location | Movement | 0.022222 | 62.3004 |  |  | N/A | In-port deployer (loaded) | Lower port | Divertor pipe modules | 8 | 0.1 | 0.022222 |  | N/A |  | N/A | N/A
| Collect MPC tooling from IPD | Logistics | 0.0492 | 62.3496 |  |  | N/A |  |  |  | N/A | N/A | N/A | Store / collect RM equipment from laydown area | 0.0492 |  | N/A | N/A
| Install MPC tooling onto the port pipework | Operation | 0.3056 | 62.6552 | Install Mechanical pipe connection tooling | Dexterous Robot Arm | 0.3056 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Actuate the MPC tooling | Operation | 0.1202 | 62.7754 | Actuate MPC tooling | MPC tooling | 0.1202 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Remove the MPC seal plug | Operation | 0.0403 | 62.8157 | Install / remove MPC seals | Dexterous robot arm | 0.0403 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Store MPC seal on the IPD | Logistics | 0.0492 | 62.8649 |  |  | N/A |  |  |  | N/A | N/A | N/A | Store / collect RM equipment from laydown area | 0.0492 |  | N/A | N/A
| Place pipe module into installed position | Logistics | 0.2126 | 63.0775 |  |  | N/A |  |  |  | N/A | N/A | N/A | Collect / store Equipment or Hardware in stillage | 0.2126 |  | N/A | N/A
| Actuate the MPC tooling to align pipe module | Operation | 0.1202 | 63.1977 | Actuate MPC tooling | MPC tooling | 0.1202 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Weld inboard pipe joints | Operation | 12.0946 | 75.2923 | Connect Divertor Pipe Module | outboard pipe module handler; SJS welding system | 12.0946 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Store SJS deployment system onto port storage location | Logistics | 0.0492 | 75.3415 |  |  | N/A |  |  |  | N/A | N/A | N/A | Store / collect RM equipment from laydown area | 0.0492 |  | N/A | N/A
| Collect pipe module inspection tooling | Logistics | 0.0492 | 75.3907 |  |  | N/A |  |  |  | N/A | N/A | N/A | Store / collect RM equipment from laydown area | 0.0492 |  | N/A | N/A
| Inspect inboard pipe module access port | Operation | 2.112 | 77.5027 | Inspect divertor pipe in-bore and pipe module interface | Dexterous robot arm | 2.112 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Store inspection tooling | Logistics | 0.0492 | 77.5519 |  |  | N/A |  |  |  | N/A | N/A | N/A | Store / collect RM equipment from laydown area | 0.0492 |  | N/A | N/A
| Collect pipe module access lid | Logistics | 0.0492 | 77.6011 |  |  | N/A |  |  |  | N/A | N/A | N/A | Store / collect RM equipment from laydown area | 0.0492 |  | N/A | N/A
| Install access port cover | Operation | 2.364 | 79.9651 | Install divertor pipe module access cover | Dexterous robot arm | 2.364 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Store fixation tooling | Logistics | 0.0492 | 80.0143 |  |  | N/A |  |  |  | N/A | N/A | N/A | Store / collect RM equipment from laydown area | 0.0492 |  | N/A | N/A
| Remove the IPD from the port | Movement | 0.022222 | 80.0365 |  |  | N/A | In-port deployer (loaded) | Divertor pipe modules | Lower Port | 8 | 0.1 | 0.022222 |  | N/A |  | N/A | N/A
Install and connect Left divetor pipe module | Transfer the pipe module from the crane to the pipe module handler | Operation | 0.0243 | 80.0608 | Actuate handling interfaces | Overhead crane; Outboard pipe module handler | 0.0243 |  |  |  | N/A | N/A | N/A |  | N/A | Return empty transport stillage to PP stores; collect new left divetor pipe module from stores; transport into lower port hot cell | 63.7896 | 16.2469
| Release the left divertor pipe module from the overhead crane | Operation | 0.0243 | 80.0851 | Actuate handling interfaces | Overhead crane; Outboard pipe module handler | 0.0243 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Deploy the IPD tractor to the divertor cassette pipe module location | Movement | 0.022222 | 80.1073 |  |  | N/A | In-port deployer (loaded) | Lower port | Divertor pipe modules | 8 | 0.1 | 0.022222 |  | N/A |  | N/A | N/A
| Remove the MPC tooling from the right divertor pipework | Operation | 0.1233 | 80.2306 | Remove MPC tooling | Dexterous Robot Arm | 0.1233 |  |  |  | N/A | N/A | N/A | Store / collect RM equipment from laydown area | N/A |  | N/A | N/A
| Install MPC tooling onto the left divertor pipework | Operation | 0.3056 | 80.5362 | Install Mechanical pipe connection tooling | Dexterous Robot Arm | 0.3056 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Actuate the MPC tooling | Operation | 0.1202 | 80.6564 | Actuate MPC tooling | MPC tooling | 0.1202 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Remove the MPC seal plug | Operation | 0.0403 | 80.6967 | Install / remove MPC seals | Dexterous robot arm | 0.0403 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Store MPC seal on the IPD | Logistics | 0.0492 | 80.7459 |  |  | N/A |  |  |  | N/A | N/A | N/A | Store / collect RM equipment from laydown area | 0.0492 |  | N/A | N/A
| Place pipe module into installed position | Logistics | 0.2126 | 80.9585 |  |  | N/A |  |  |  | N/A | N/A | N/A | Collect / store Equipment or Hardware in stillage | 0.2126 |  | N/A | N/A
| Actuate the MPC tooling to align pipe module | Operation | 0.1202 | 81.0787 | Actuate MPC tooling | MPC tooling | 0.1202 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Collect SJS deployment system from port storage location | Logistics | 0.0492 | 81.1279 |  |  | N/A |  |  |  | N/A | N/A | N/A | Store / collect RM equipment from laydown area | 0.0492 |  | N/A | N/A
| Weld inboard pipe joints | Operation | 12.0946 | 93.2225 | Connect Divertor Pipe Module | outboard pipe module handler; SJS welding system | 12.0946 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Store SJS deployment system onto port storage location | Logistics | 0.0492 | 93.2717 |  |  | N/A |  |  |  | N/A | N/A | N/A | Store / collect RM equipment from laydown area | 0.0492 |  | N/A | N/A
| Collect pipe module inspection tooling | Logistics | 0.0492 | 93.3209 |  |  | N/A |  |  |  | N/A | N/A | N/A | Store / collect RM equipment from laydown area | 0.0492 |  | N/A | N/A
| Inspect inboard pipe module access port | Operation | 2.112 | 95.4329 | Inspect divertor pipe in-bore and pipe module interface | Dexterous robot arm | 2.112 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Store inspection tooling | Logistics | 0.0492 | 95.4821 |  |  | N/A |  |  |  | N/A | N/A | N/A | Store / collect RM equipment from laydown area | 0.0492 |  | N/A | N/A
| Collect pipe module access lid | Logistics | 0.0492 | 95.5313 |  |  | N/A |  |  |  | N/A | N/A | N/A | Store / collect RM equipment from laydown area | 0.0492 |  | N/A | N/A
| Install access port cover | Operation | 2.364 | 97.8953 | Install divertor pipe module access cover | Dexterous robot arm | 2.364 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Store fixation tooling | Logistics | 0.0492 | 97.9445 |  |  | N/A |  |  |  | N/A | N/A | N/A | Store / collect RM equipment from laydown area | 0.0492 |  | N/A | N/A
| Remove the IPD from the port | Movement | 0.022222 | 97.9668 |  |  | N/A | In-port deployer (loaded) | Divertor pipe modules | Lower Port | 8 | 0.1 | 0.022222 |  | N/A |  | N/A | N/A
Install and connect Centre divetor pipe module | Transfer the pipe module from the crane to the pipe module handler | Operation | 0.0243 | 97.9911 | Actuate handling interfaces | Overhead crane; Outboard pipe module handler | 0.0243 |  |  |  | N/A | N/A | N/A |  | N/A | Return empty transport stillage to PP stores; collect new centre divetor pipe module from stores; transport into lower port hot cell | 81.5966 | 16.3702
| Release the centre pipe module from the overhead crane | Operation | 0.0243 | 98.0154 | Actuate handling interfaces | Overhead crane; Outboard pipe module handler | 0.0243 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Deploy the IPD tractor to the divertor cassette pipe module location | Movement | 0.022222 | 98.0376 |  |  | N/A | In-port deployer (loaded) | Lower port | Divertor pipe modules | 8 | 0.1 | 0.022222 |  | N/A |  | N/A | N/A
| Collect MPC tooling from IPD | Logistics | 0.0492 | 98.0868 |  | Dexterous Robot Arm | N/A |  |  |  | N/A | N/A | N/A | Store / collect RM equipment from laydown area | 0.0492 |  | N/A | N/A
| Install MPC tooling onto the port pipework | Operation | 0.3056 | 98.3924 | Install Mechanical pipe connection tooling | Dexterous Robot Arm | 0.3056 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Actuate the MPC tooling | Operation | 0.1202 | 98.5126 | Actuate MPC tooling | MPC tooling | 0.1202 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Remove the MPC seal plug | Operation | 0.0403 | 98.5529 | Install / remove MPC seals | Dexterous robot arm | 0.0403 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Store MPC seal on the IPD | Logistics | 0.0492 | 98.6021 |  |  | N/A |  |  |  | N/A | N/A | N/A | Store / collect RM equipment from laydown area | 0.0492 |  | N/A | N/A
| Place pipe module into installed position | Logistics | 0.2126 | 98.8147 |  |  | N/A |  |  |  | N/A | N/A | N/A | Collect / store Equipment or Hardware in stillage | 0.2126 |  | N/A | N/A
| Actuate the MPC tooling to align pipe module | Operation | 0.1202 | 98.9349 | Actuate MPC tooling | MPC tooling | 0.1202 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Collect SJS deployment system from port storage location | Logistics | 0.0492 | 98.9841 |  |  | N/A |  |  |  | N/A | N/A | N/A | Store / collect RM equipment from laydown area | 0.0492 |  | N/A | N/A
| Weld inboard pipe joints | Operation | 12.0946 | 111.0787 | Connect Divertor Pipe Module | outboard pipe module handler; SJS welding system | 12.0946 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Store SJS deployment system onto port storage location | Logistics | 0.0492 | 111.1279 |  |  | N/A |  |  |  | N/A | N/A | N/A | Store / collect RM equipment from laydown area | 0.0492 |  | N/A | N/A
| Collect pipe module inspection tooling | Logistics | 0.0492 | 111.1771 |  |  | N/A |  |  |  | N/A | N/A | N/A | Store / collect RM equipment from laydown area | 0.0492 |  | N/A | N/A
| Inspect inboard pipe module access port | Operation | 2.112 | 113.2891 | Inspect divertor pipe in-bore and pipe module interface | Dexterous robot arm | 2.112 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Store inspection tooling | Logistics | 0.0492 | 113.3383 |  |  | N/A |  |  |  | N/A | N/A | N/A | Store / collect RM equipment from laydown area | 0.0492 |  | N/A | N/A
| Collect pipe module access lid | Logistics | 0.0492 | 113.3875 |  |  | N/A |  |  |  | N/A | N/A | N/A | Store / collect RM equipment from laydown area | 0.0492 |  | N/A | N/A
| Install access port cover | Operation | 2.364 | 115.7515 | Install divertor pipe module access cover | Dexterous robot arm | 2.364 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Store fixation tooling | Logistics | 0.0492 | 115.8007 |  |  | N/A |  |  |  | N/A | N/A | N/A | Store / collect RM equipment from laydown area | 0.0492 |  | N/A | N/A
| Move arm to the MPC location | Logistics | 0.38 | 116.1807 |  |  | N/A |  |  |  | N/A | N/A | N/A | Reposition tool within Port | 0.38 |  | N/A | N/A
| Remove the MPC tooling from the pipe module | Operation | 0.1233 | 116.304 | Remove MPC tooling | Dexterous robot arm | 0.1233 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Store on the IPD | Logistics | 0.0492 | 116.3532 |  |  | N/A |  |  |  | N/A | N/A | N/A | Store / collect RM equipment from laydown area | 0.0492 |  | N/A | N/A
| Collect SJS deployment system from the port storage location | Logistics | 0.0492 | 116.4024 |  |  | N/A |  |  |  | N/A | N/A | N/A | Store / collect RM equipment from laydown area | 0.0492 |  | N/A | N/A
| Return the IPD to the rear of the threshold rails | Movement | 0.0083333 | 116.4107 |  |  | N/A | In-port deployer (loaded) | Vacuum pumping equipment | Lower Port | 3 | 0.1 | 0.0083333 |  | N/A |  | N/A | N/A
Store lower port pipework tooling | Move MPR to the IPD trailers | Movement | 0.00066934 | 116.4114 |  |  | N/A | Multi-purpose robot (transport) | RM tool storage | Lower Port | 2 | 0.83 | 0.00066934 |  | N/A |  | N/A | N/A
| Transfer SJS deployment system to the MPR | Logistics | 0.0492 | 116.4606 |  |  | N/A |  |  |  | N/A | N/A | N/A | Store / collect RM equipment from laydown area | 0.0492 |  | N/A | N/A
| Move MPR to the SJS service cask | Movement | 0.0026774 | 116.4633 |  |  | N/A | Multi-purpose robot (transport) | Lower port | RM equipment stillage | 8 | 0.83 | 0.0026774 |  | N/A |  | N/A | N/A
| Store SJS deployment system in the service cask | Logistics | 0.0492 | 116.5125 |  |  | N/A |  |  |  | N/A | N/A | N/A | Store / collect RM equipment from laydown area | 0.0492 |  | N/A | N/A
| Move MPR back to the IPD trailer | Movement | 0.0026774 | 116.5152 |  |  | N/A | Multi-purpose robot (transport) | RM equipment stillage | Lower Port | 8 | 0.83 | 0.0026774 |  | N/A |  | N/A | N/A
| Decouple the pipe module handler from IPD | Operation | 0.134 | 116.6492 | Couple / decouple IPD movers | MPR | 0.134 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Collect the pipe module handler using the overhead crane | Logistics | 0.336 | 116.9852 |  |  | N/A |  |  |  | N/A | N/A | N/A | Store / collect items with the overhead crane | 0.336 |  | N/A | N/A
| Transfer to the hot cell interface | Movement | 0.18056 | 117.1657 |  |  | N/A | Overhead crane (loaded) | Lower port | Hot Cell Interface | 13 | 0.02 | 0.18056 |  | N/A |  | N/A | N/A
| Deposit outboard pipe module handler on the hot cell interface | Logistics | 0.336 | 117.5017 |  |  | N/A |  |  |  | N/A | N/A | N/A | Store / collect items with the overhead crane | 0.336 | Return empty centre div pipe module transport stillage to PP stores; return empty transport into lower port hot cell | 98.6324 | 18.5333
Remove SJS cask from the hot cell | Move overehead crane to the SJS service cask | Movement | 0.0069444 | 119.4198 |  |  | N/A | Overhead crane (unloaded) | RM tool storage | RM equipment stillage | 5 | 0.2 | 0.0069444 |  | N/A | Collect pipe module tooling and equipment for hot cell; transport to long term RM storage; store pipe module tooling; collect generic RM equipment and return transporter to hot cell | 119.4129 | -1.9112
| Collect SJS cask | Logistics | 0.336 | 119.7558 |  |  | N/A |  |  |  | N/A | N/A | N/A | Store / collect items with the overhead crane | 0.336 |  | N/A | N/A
| Move SJS cask to the hot cell interface | Movement | 0.083333 | 119.8392 |  |  | N/A | Overhead crane (loaded) | RM equipment stillage | Hot Cell Interface | 6 | 0.02 | 0.083333 |  | N/A |  | N/A | N/A
| Place SJS cask onto the hot cell interface | Logistics | 0.336 | 120.1752 |  |  | N/A |  |  |  | N/A | N/A | N/A | Store / collect items with the overhead crane | 0.336 |  | N/A | N/A
Replace robot arm from the IPD in preparation to remove the threshold rails | Move overhead crane to the lower port interface | Movement | 0.018056 | 120.1932 |  |  | N/A | Overhead crane (unloaded) | Hot Cell Interface | Lower Port | 13 | 0.2 | 0.018056 |  | N/A |  | N/A | N/A
| Decouple the IPD trailer from the IPD system | Operation | 0.134 | 120.3272 | Couple / decouple IPD movers | MPR | 0.134 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Remove the IPD trailer from the port | Logistics | 0.336 | 120.6632 |  |  | N/A |  |  |  | N/A | N/A | N/A | Store / collect items with the overhead crane | 0.336 |  | N/A | N/A
| Transport the IPD trailer to the RM equipment laydown area | Movement | 0.11111 | 120.7743 |  |  | N/A | Overhead crane (loaded) | Lower port | RM equipment stillage | 8 | 0.02 | 0.11111 |  | N/A |  | N/A | N/A
| Store the tractor in the laydown area | Logistics | 0.336 | 121.1103 |  |  | N/A |  |  |  | N/A | N/A | N/A | Store / collect items with the overhead crane | 0.336 |  | N/A | N/A
| Move overehead crane to robot arm storage area | Movement | 0.011111 | 121.1214 |  |  | N/A | Overhead crane (unloaded) | RM equipment stillage | RM robot arm storage | 8 | 0.2 | 0.011111 |  | N/A |  | N/A | N/A
| Collect robot arm lifting frame | Logistics | 0.336 | 121.4574 |  |  | N/A |  |  |  | N/A | N/A | N/A | Store / collect items with the overhead crane | 0.336 |  | N/A | N/A
| Move overhead crane to lower port | Movement | 0.22222 | 121.6797 |  |  | N/A | Overhead crane (loaded) | RM robot arm storage | Lower Port | 16 | 0.02 | 0.22222 |  | N/A |  | N/A | N/A
| Remove the robot arm from the IPD | Logistics | 0.336 | 122.0157 |  |  | N/A |  |  |  | N/A | N/A | N/A | Store / collect items with the overhead crane | 0.336 |  | N/A | N/A
| Move robot arm to storage location | Movement | 0.22222 | 122.2379 |  |  | N/A | Overhead crane (loaded) | Lower port | RM robot arm storage | 16 | 0.02 | 0.22222 |  | N/A |  | N/A | N/A
| Store dexterous arm | Logistics | 0.336 | 122.5739 |  |  | N/A |  |  |  | N/A | N/A | N/A | Store / collect items with the overhead crane | 0.336 |  | N/A | N/A
| Collect high payload long reach robot arm from the storage frame | Logistics | 0.336 | 122.9099 |  |  | N/A |  |  |  | N/A | N/A | N/A | Store / collect items with the overhead crane | 0.336 |  | N/A | N/A
| Move overhead crane to lower port | Movement | 0.22222 | 123.1321 |  |  | N/A | Overhead crane (loaded) | RM robot arm storage | Lower Port | 16 | 0.02 | 0.22222 |  | N/A |  | N/A | N/A
| Install and commission the high payload arm on the IPD | Operation | 2.332 | 125.4641 | Install and commission robot arm into an IPD mover | MPR; IPD | 2.332 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
Remove divertor gauge rails from the hot cell | Deploy IPD into the port | Movement | 0.0083333 | 125.4724 |  |  | N/A | In-port deployer (loaded) | Lower port | Vacuum pumping equipment | 3 | 0.1 | 0.0083333 |  | N/A |  | N/A | N/A
| Couple the threshold rails to the IPD | Operation | 0.134 | 125.6064 | Couple / decouple IPD movers | High payload arm; IPD | 0.134 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Release divertor gauge rail installation fixations | Operation | 0.702 | 126.3084 | Remove demountable port rails | High payload arm; | 0.702 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Remove rails from the port | Movement | 0.0083333 | 126.3168 |  |  | N/A | In-port deployer (loaded) | Vacuum pumping equipment | Lower Port | 3 | 0.1 | 0.0083333 |  | N/A |  | N/A | N/A
| Decouple the rails from the IPD | Operation | 0.134 | 126.4508 | Couple / decouple IPD movers | High payload arm; IPD | 0.134 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Collect the divertor gauge rails with the overhead rails | Logistics | 0.336 | 126.7868 |  |  | N/A |  |  |  | N/A | N/A | N/A | Store / collect items with the overhead crane | 0.336 |  | N/A | N/A
| Move rails to the port interface | Movement | 0.18056 | 126.9673 |  |  | N/A | Overhead crane (loaded) | Lower port | Hot Cell Interface | 13 | 0.02 | 0.18056 |  | N/A |  | N/A | N/A
| Deposit divertor gauge rails on the hot cell interface | Logistics | 0.336 | 127.3033 |  |  | N/A |  |  |  | N/A | N/A | N/A | Store / collect items with the overhead crane | 0.336 | Remove SJS cask from the hot cell; store cask and return transporter to the hot cell | N/A | N/A
Inspection revealed in-port area | Move inspection tooling into the RM storage location | Movement | 0.0083333 | 127.3117 |  |  | N/A | In-port deployer (loaded) | Lower Port | Vacuum pumping equipment | 3 | 0.1 | 0.0083333 |  | N/A |  | N/A | N/A
| Collect in-port inspection tooling | Logistics | 0.0492 | 127.3609 |  |  | N/A |  |  |  | N/A | N/A | N/A | Store / collect RM equipment from laydown area | 0.0492 |  | N/A | N/A
| Commission in-port inspection tooling | Logistics | 0.6233 | 127.9842 |  |  | N/A |  |  |  | N/A | N/A | N/A | Make and commission RM service connections | 0.6233 |  | N/A | N/A
| Move inspection tooling into the port | Movement | 0.0083333 | 127.9925 |  |  | N/A | In-port deployer (loaded) | Lower port | Vacuum pumping equipment | 3 | 0.1 | 0.0083333 |  | N/A |  | N/A | N/A
| Inspect revealed port liner | Operation | 0.36361 | 128.3561 | Inspect revealed area of the lower port | IPD; High Payload arm | 0.36361 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Remove inspection system from the port | Movement | 0.036111 | 128.3922 |  |  | N/A | In-port deployer (loaded) | Vacuum pumping equipment | RM tool storage | 13 | 0.1 | 0.036111 |  | N/A |  | N/A | N/A
| Return inspection tooling to RM storage | Logistics | 0.0492 | 128.4414 |  |  | N/A |  |  |  | N/A | N/A | N/A | Store / collect RM equipment from laydown area | 0.0492 |  | N/A | N/A
| Return IPD tractor to the lower port interface | Movement | 0.0055556 | 128.447 |  |  | N/A | In-port deployer (loaded) | RM tool storage | Lower Port | 2 | 0.1 | 0.0055556 |  | N/A |  | N/A | N/A
Re-install the vacuum pump assembly | Move overhead crane to the PP hardware stillage | Movement | 0.0083333 | 128.4553 |  |  | N/A | Overhead crane (unloaded) | Hot Cell Interface | PP hardware stillage | 6 | 0.2 | 0.0083333 |  | N/A |  | N/A | N/A
| Collect Vacuum pumping assembly from storage | Logistics | 0.2126 | 128.6679 |  |  | N/A |  |  |  | N/A | N/A | N/A | Collect / store Equipment or Hardware in stillage | 0.2126 |  | N/A | N/A
| Move vacuum pumping assembly to the lower port | Movement | 0.13889 | 128.8068 |  |  | N/A | Overhead crane (loaded) | PP hardware stillage | Lower Port | 10 | 0.02 | 0.13889 |  | N/A |  | N/A | N/A
| Place vacuum pumping equipment onto the threshold rails | Logistics | 0.336 | 129.1428 |  |  | N/A |  |  |  | N/A | N/A | N/A | Store / collect items with the overhead crane | 0.336 |  | N/A | N/A
| Remove the contamination control barrier from the vacuum pump | Operation | 0.352 | 129.4948 | Remove vacuum pump contamination control barrier | MPR | 0.352 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Couple the vacuum pump to the IPD | Operation | 0.134 | 129.6288 | Couple / decouple IPD movers | MPR; IPD | 0.134 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Move the vacuum pumping assembly into its installed locations | Movement | 0.0083333 | 129.6371 |  |  | N/A | In-port deployer (loaded) | Lower port | Vacuum pumping equipment | 3 | 0.1 | 0.0083333 |  | N/A |  | N/A | N/A
| Install vacuum pump fixations | Operation | 0.57211 | 130.2092 | Release vacuum fixation tooling | High Payload arm; IPD | 0.57211 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Lower the vacuum pump into its installed position | Operation | 0.102 | 130.3112 | Actuate vacuum pump wheel jacks | Vacuum pump wheel jacks | 0.102 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Remove rear wheel jacks | Operation | 0.45405 | 130.7653 | Remove Vacuum pump front wheel jacks | In-port rover | 0.45405 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Deploy in-port rover to the front of the vaccum pump | Operation | 0.268 | 131.0333 | Remove Vacuum pump rear wheel jacks | High Payload arm | 0.268 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Decouple the vacuum pump front the IPD | Operation | 0.134 | 131.1673 | Couple / decouple IPD movers | High Payload arm | 0.134 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Move IPD system to the rear of the threshold rails | Movement | 0.0083333 | 131.1756 |  |  | N/A | In-port deployer (loaded) | Vacuum pumping equipment | Lower Port | 3 | 0.1 | 0.0083333 |  | N/A |  | N/A | N/A
Remove all vacuum pump handling equipment from the hot cell | Collect wheel jacks with the MPR | Logistics | 0.0492 | 131.2248 |  |  | N/A |  |  |  | N/A | N/A | N/A | Store / collect RM equipment from laydown area | 0.0492 |  | N/A | N/A
| Move MPR to the appropriate tool sotrage locations | Movement | 0.0026774 | 131.2275 |  |  | N/A | Multi-purpose robot (transport) | Lower port | RM equipment stillage | 8 | 0.83 | 0.0026774 |  | N/A |  | N/A | N/A
| Store wheel jacks | Logistics | 0.0492 | 131.2767 |  |  | N/A |  |  |  | N/A | N/A | N/A | Store / collect RM equipment from laydown area | 0.0492 |  | N/A | N/A
| Return to the IPD tractor | Movement | 0.0026774 | 131.2794 |  |  | N/A | Multi-purpose robot (transport) | RM equipment stillage | Lower Port | 8 | 0.83 | 0.0026774 |  | N/A |  | N/A | N/A
| Collect vacuum pumping fixation tooling from IPD | Logistics | 0.0492 | 131.3286 |  |  | N/A |  |  |  | N/A | N/A | N/A | Store / collect RM equipment from laydown area | 0.0492 |  | N/A | N/A
| Return to tool storage location | Movement | 0.0026774 | 131.3313 |  |  | N/A | Multi-purpose robot (transport) | Lower port | RM equipment stillage | 8 | 0.83 | 0.0026774 |  | N/A |  | N/A | N/A
| Store fixation tooling | Logistics | 0.0492 | 131.3805 |  |  | N/A |  |  |  | N/A | N/A | N/A | Store / collect RM equipment from laydown area | 0.0492 |  | N/A | N/A
| Move MPR to threshold rails | Movement | 0.0026774 | 131.3831 |  |  | N/A | Multi-purpose robot (transport) | RM equipment stillage | Lower Port | 8 | 0.83 | 0.0026774 |  | N/A |  | N/A | N/A
| Collect in-port rover from the rails | Logistics | 0.0492 | 131.4323 |  |  | N/A |  |  |  | N/A | N/A | N/A | Store / collect RM equipment from laydown area | 0.0492 |  | N/A | N/A
| Move to the hot cell interface | Movement | 0.0043507 | 131.4367 |  |  | N/A | Multi-purpose robot (transport) | Lower port | Hot Cell Interface | 13 | 0.83 | 0.0043507 |  | N/A |  | N/A | N/A
| Transfer the in-port rover to the hot cell interface | Logistics | 0.0492 | 131.4859 |  |  | N/A |  |  |  | N/A | N/A | N/A | Store / collect RM equipment from laydown area | 0.0492 |  | N/A | N/A
| Move overhead crane to the tool storage location | Movement | 0.011111 | 131.497 |  |  | N/A | Overhead crane (unloaded) | Lower port | RM equipment stillage | 8 | 0.2 | 0.011111 |  | N/A |  | N/A | N/A
| Collect the vacuum pump tooling storage | Logistics | 0.336 | 131.833 |  |  | N/A |  |  |  | N/A | N/A | N/A | Store / collect items with the overhead crane | 0.336 |  | N/A | N/A
| Move to the hot cell interface | Movement | 0.083333 | 131.9163 |  |  | N/A | Overhead crane (loaded) | RM equipment stillage | Hot Cell Interface | 6 | 0.02 | 0.083333 |  | N/A |  | N/A | N/A
| Place tool storage on the hot cell interface | Logistics | 0.336 | 132.2523 |  |  | N/A |  |  |  | N/A | N/A | N/A | Store / collect items with the overhead crane | 0.336 |  | N/A | N/A
| Transfer vacuum pumping RM equipment out of the hot cell | Logistics | 0.214 | 132.4663 |  |  | N/A |  |  |  | N/A | N/A | N/A | Transfer equipment to/from port interface | 0.214 | Remove and store divertor gauge rails; return ex-vessel hardware to collect more RM equipment from the hot cell | 127.9204 | 4.3319
Install vacuum pump pipe module | Move MPR to the tool storage location | Movement | 0.0033467 | 132.4697 |  |  | N/A | Multi-purpose robot (transport) | Hot Cell Interface | RM tool storage | 10 | 0.83 | 0.0033467 |  | N/A |  | N/A | N/A
| Collect MPC tooling from storage location | Logistics | 0.0492 | 132.5189 |  |  | N/A |  |  |  | N/A | N/A | N/A | Store / collect RM equipment from laydown area | 0.0492 |  | N/A | N/A
| Transport MPC tooling to the IPD system | Movement | 0.00066934 | 132.5195 |  |  | N/A | Multi-purpose robot (transport) | RM tool storage | Lower Port | 2 | 0.83 | 0.00066934 |  | N/A |  | N/A | N/A
| Transfer MPC tooling to the IPD | Logistics | 0.0492 | 132.5687 |  |  | N/A |  |  |  | N/A | N/A | N/A | Store / collect RM equipment from laydown area | 0.0492 |  | N/A | N/A
| Move IPD to the rear of the vacuum pump | Movement | 0.0083333 | 132.5771 |  |  | N/A | In-port deployer (loaded) | Lower port | Vacuum pumping equipment | 3 | 0.1 | 0.0083333 |  | N/A |  | N/A | N/A
| Install first MPC tooling onto the pipe stubs | Operation | 0.3056 | 132.8827 | Install Mechanical pipe connection tooling | High payload arm; MPC tooling | 0.3056 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Remove the first pipe stub seal | Operation | 0.0403 | 132.923 | Install / remove MPC seals | High payload arm; MPC tooling | 0.0403 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Store on the IPD | Logistics | 0.0492 | 132.9722 |  |  | N/A |  |  |  | N/A | N/A | N/A | Store / collect RM equipment from laydown area | 0.0492 |  | N/A | N/A
| Install the second MPC tooling | Operation | 0.3056 | 133.2778 | Install Mechanical pipe connection tooling | High payload arm; MPC tooling | 0.3056 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Remove the second MPC seal from the pipe stub | Operation | 0.0403 | 133.3181 | Install / remove MPC seals | High payload arm; MPC tooling | 0.0403 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Store pipe seals in the IPD | Logistics | 0.0492 | 133.3673 |  |  | N/A |  |  |  | N/A | N/A | N/A | Store / collect RM equipment from laydown area | 0.0492 |  | N/A | N/A
| Return the IPD to the rear of the threshold rails | Movement | 0.0083333 | 133.3756 |  |  | N/A | In-port deployer (loaded) | Vacuum pumping equipment | Lower Port | 3 | 0.1 | 0.0083333 |  | N/A |  | N/A | N/A
| Collect the divertor pipe module from next to the port | Logistics | 0.0492 | 133.4248 |  |  | N/A |  |  |  | N/A | N/A | N/A | Store / collect RM equipment from laydown area | 0.0492 |  | N/A | N/A
| Move IPD back into the port | Movement | 0.0083333 | 133.4331 |  |  | N/A | In-port deployer (loaded) | Lower port | Vacuum pumping equipment | 3 | 0.1 | 0.0083333 |  | N/A |  | N/A | N/A
| Place the new vacuum pipe module into its installed position | Logistics | 0.2126 | 133.6457 |  |  | N/A |  |  |  | N/A | N/A | N/A | Collect / store Equipment or Hardware in stillage | 0.2126 |  | N/A | N/A
| Actuate the first MPC joint | Operation | 0.1202 | 133.7659 | Actuate MPC tooling | MPC tooling | 0.1202 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Actuate the Second MPC joint | Operation | 0.1202 | 133.8861 | Actuate MPC tooling | MPC tooling | 0.1202 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Collect a MPC tooling from the pipe joint | Operation | 0.3056 | 134.1917 | Install Mechanical pipe connection tooling | High payload arm; MPC tooling | 0.3056 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Store MPC tooling on the IPD | Logistics | 0.0492 | 134.2409 |  |  | N/A |  |  |  | N/A | N/A | N/A | Store / collect RM equipment from laydown area | 0.0492 |  | N/A | N/A
| Collect a MPC tooling from the pipe joint | Operation | 0.3056 | 134.5465 | Install Mechanical pipe connection tooling | High payload arm; MPC tooling | 0.3056 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Move the IPD out from the port | Movement | 0.0083333 | 134.5549 |  |  | N/A | In-port deployer (loaded) | Vacuum pumping equipment | Lower Port | 3 | 0.1 | 0.0083333 |  | N/A |  | N/A | N/A
Remove RM tooling and threshold rails from the port | Move overhead crane to the ROM tool storage location | Movement | 0.013889 | 134.5688 |  |  | N/A | Overhead crane (unloaded) | Hot Cell Interface | RM tool storage | 10 | 0.2 | 0.013889 |  | N/A |  | N/A | N/A
| Collect RM tool storage | Logistics | 0.336 | 134.9048 |  |  | N/A |  |  |  | N/A | N/A | N/A | Store / collect items with the overhead crane | 0.336 |  | N/A | N/A
| Move overhead crane to the hot cell interface | Movement | 0.13889 | 135.0437 |  |  | N/A | Overhead crane (loaded) | RM tool storage | Hot Cell Interface | 10 | 0.02 | 0.13889 |  | N/A |  | N/A | N/A
| Deposit RM tool storage onto the hot cell interface | Logistics | 0.336 | 135.3797 |  |  | N/A |  |  |  | N/A | N/A | N/A | Store / collect items with the overhead crane | 0.336 |  | N/A | N/A
| Move overhead crane to robot arm storage | Movement | 0.0027778 | 135.3824 |  |  | N/A | Overhead crane (unloaded) | Hot Cell Interface | RM robot arm storage | 2 | 0.2 | 0.0027778 |  | N/A |  | N/A | N/A
| Collect robot arm lifting frame | Logistics | 0.336 | 135.7184 |  |  | N/A |  |  |  | N/A | N/A | N/A | Store / collect items with the overhead crane | 0.336 |  | N/A | N/A
| Move to threshold rails | Movement | 0.22222 | 135.9407 |  |  | N/A | Overhead crane (loaded) | RM robot arm storage | Lower Port | 16 | 0.02 | 0.22222 |  | N/A |  | N/A | N/A
| Remove high payload arm off the IPD tractor | Operation | 0.418 | 136.3587 | Remove robot arm from the IPD | Overhead crane; IPD; MPR | 0.418 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Transport to the robot arm stillage | Movement | 0.22222 | 136.5809 |  |  | N/A | Overhead crane (loaded) | Lower port | RM robot arm storage | 16 | 0.02 | 0.22222 |  | N/A |  | N/A | N/A
| Store the high payload arm in the stillage | Logistics | 0.336 | 136.9169 |  |  | N/A |  |  |  | N/A | N/A | N/A | Store / collect items with the overhead crane | 0.336 |  | N/A | N/A
| Move overhead crane to the threshold rails | Movement | 0.022222 | 136.9391 |  |  | N/A | Overhead crane (unloaded) | RM robot arm storage | Lower Port | 16 | 0.2 | 0.022222 |  | N/A |  | N/A | N/A
| Collect the IPD trailer from the threshold rails | Logistics | 0.336 | 137.2751 |  |  | N/A |  |  |  | N/A | N/A | N/A | Store / collect items with the overhead crane | 0.336 |  | N/A | N/A
| Move to the hot cell interface | Movement | 0.18056 | 137.4557 |  |  | N/A | Overhead crane (loaded) | Lower port | Hot Cell Interface | 13 | 0.02 | 0.18056 |  | N/A |  | N/A | N/A
| Place tractor onto the hot cell interface for removal from the hot cell | Logistics | 0.336 | 137.7917 |  |  | N/A |  |  |  | N/A | N/A | N/A | Store / collect items with the overhead crane | 0.336 | Remove and store vacuum pumping tooling; return ex-vessel hardware to collect more RM equipment from the hot cell | 133.0834 | 4.3723
| Move overhead crane to the RM tool storage | Movement | 0.0083333 | 137.8 |  |  | N/A | Overhead crane (unloaded) | Hot Cell Interface | RM equipment stillage | 6 | 0.2 | 0.0083333 |  | N/A |  | N/A | N/A
| Collect robot arm end effector storage | Logistics | 0.336 | 138.136 |  |  | N/A |  |  |  | N/A | N/A | N/A | Store / collect items with the overhead crane | 0.336 |  | N/A | N/A
| Move to the hot cell interface | Movement | 0.083333 | 138.2193 |  |  | N/A | Overhead crane (loaded) | RM equipment stillage | Hot Cell Interface | 6 | 0.02 | 0.083333 |  | N/A |  | N/A | N/A
| Depsoit robot arm end effector storage | Logistics | 0.336 | 138.5553 |  |  | N/A |  |  |  | N/A | N/A | N/A | Store / collect items with the overhead crane | 0.336 |  | N/A | N/A
| Move overhead crane to the RM robot arm storage | Movement | 0.0027778 | 138.5581 |  |  | N/A | Overhead crane (unloaded) | Hot Cell Interface | RM robot arm storage | 2 | 0.2 | 0.0027778 |  | N/A |  | N/A | N/A
| Collect robot arm stillage | Logistics | 0.336 | 138.8941 |  |  | N/A |  |  |  | N/A | N/A | N/A | Store / collect items with the overhead crane | 0.336 |  | N/A | N/A
| Move to the hot cell interface | Movement | 0.027778 | 138.9219 |  |  | N/A | Overhead crane (loaded) | RM robot arm storage | Hot Cell Interface | 2 | 0.02 | 0.027778 |  | N/A |  | N/A | N/A
| Deposit robot arm stillage on the interface | Logistics | 0.336 | 139.2579 |  |  | N/A |  |  |  | N/A | N/A | N/A | Store / collect items with the overhead crane | 0.336 | Remove and store IPD tractor and robot arm end effectors; return ex-vessel hardware to collect more RM equipment from the hot cell | 138.4087 | 0.51315
Dismantle the In-port deployment system | Move overhead crane to the lower port | Movement | 0.018056 | 139.2759 |  |  | N/A | Overhead crane (unloaded) | Hot Cell Interface | Lower Port | 13 | 0.2 | 0.018056 |  | N/A |  | N/A | N/A
| Using the MPR, decouple the IPD tractor from the threshold rails | Operation | 0.822 | 140.0979 | Decomission the IPD chain and tractor systems | MPR | 0.822 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Collect the tractor with the overhead crane | Logistics | 0.336 | 140.4339 |  |  | N/A |  |  |  | N/A | N/A | N/A | Store / collect items with the overhead crane | 0.336 |  | N/A | N/A
| Move to the hot cell interface | Movement | 0.18056 | 140.6145 |  |  | N/A | Overhead crane (loaded) | Lower port | Hot Cell Interface | 13 | 0.02 | 0.18056 |  | N/A |  | N/A | N/A
| Deposit tractor on the interface | Logistics | 0.336 | 140.9505 |  |  | N/A |  |  |  | N/A | N/A | N/A | Store / collect items with the overhead crane | 0.336 |  | N/A | N/A
| Move overhead crane to the lower port | Movement | 0.018056 | 140.9685 |  |  | N/A | Overhead crane (unloaded) | Hot Cell Interface | Lower Port | 13 | 0.2 | 0.018056 |  | N/A |  | N/A | N/A
| Collect the IPD chain assembly from the rails | Logistics | 0.336 | 141.3045 |  |  | N/A |  |  |  | N/A | N/A | N/A | Store / collect items with the overhead crane | 0.336 |  | N/A | N/A
| Move IPD chain to the hot cell interface | Movement | 0.18056 | 141.4851 |  |  | N/A | Overhead crane (loaded) | Lower port | Hot Cell Interface | 13 | 0.02 | 0.18056 |  | N/A |  | N/A | N/A
| Deposit chain onto the hot cell interface | Logistics | 0.336 | 141.8211 |  |  | N/A |  |  |  | N/A | N/A | N/A | Store / collect items with the overhead crane | 0.336 |  | N/A | N/A
Remove the threshold rails from the port mouth | Move MPR to the rear threshold rail fixation | Movement | 0.00066934 | 141.8218 |  |  | N/A | Multi-purpose robot (transport) | Lower port | RM tool storage | 2 | 0.83 | 0.00066934 |  | N/A |  | N/A | N/A
| Remove threshold rail fixations | Operation | 0.702 | 142.5238 | Remove demountable port rails | MPR | 0.702 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Move MPR to the rear of the threhsold rails | Movement | 0.0016734 | 142.5254 |  |  | N/A | Multi-purpose robot (transport) | RM tool storage | RM equipment stillage | 5 | 0.83 | 0.0016734 |  | N/A |  | N/A | N/A
| Couple the MPR to the threshold rails | Operation | 0.134 | 142.6594 | Couple / decouple IPD movers | MPR | 0.134 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Actuate the threshold rails wheel jacks | Operation | 0.086 | 142.7454 | Actuate wheel jacks | Threshold rails | 0.086 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Move the threshold rails away from the inner port rails | Movement | 0.0016734 | 142.7471 |  |  | N/A | Multi-purpose robot (transport) | RM equipment stillage | RM tool storage | 5 | 0.83 | 0.0016734 |  | N/A |  | N/A | N/A
| Uncouple the MPR from the rails | Operation | 0.134 | 142.8811 | Couple / decouple IPD movers | MPR | 0.134 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Collect outer rails with the overhead crane | Logistics | 0.336 | 143.2171 |  |  | N/A |  |  |  | N/A | N/A | N/A | Store / collect items with the overhead crane | 0.336 |  | N/A | N/A
| Move rails to the hot cell interface | Movement | 0.18056 | 143.3977 |  |  | N/A | Overhead crane (loaded) | Lower port | Hot Cell Interface | 13 | 0.02 | 0.18056 |  | N/A | Remove and store IPD tractor and robot arm end effectors; return ex-vessel hardware to collect more RM equipment from the hot cell | 138.4087 | 4.8084
| Deposit rear threshold rails onto hot cell interface | Logistics | 0.336 | 143.7337 |  |  | N/A |  |  |  | N/A | N/A | N/A | Store / collect items with the overhead crane | 0.336 |  | N/A | N/A
| Move overhead crane to the lower port | Movement | 0.018056 | 143.7517 |  |  | N/A | Overhead crane (unloaded) | Hot Cell Interface | Lower Port | 13 | 0.2 | 0.018056 |  | N/A |  | N/A | N/A
| Collect the inner set of threshold rails | Logistics | 0.336 | 144.6131 |  |  | N/A |  |  |  | N/A | N/A | N/A | Store / collect items with the overhead crane | 0.336 | Move MPR to the inner set of threshold rails; release fixations and move rails away from the port interface | 144.2771 | -0.5254
| Move second set of rails to the hot cell interface | Movement | 0.18056 | 144.7937 |  |  | N/A | Overhead crane (loaded) | Lower port | Hot Cell Interface | 13 | 0.02 | 0.18056 |  | N/A |  | N/A | N/A
| Deposit inner threshold rails onto the port interface | Logistics | 0.336 | 145.1297 |  |  | N/A |  |  |  | N/A | N/A | N/A | Store / collect items with the overhead crane | 0.336 | Remove and store outer set of threshold rails; return ex-vessel hardware to collect more RM equipment from the hot cell | 144.3507 | 0.44295
Seal vacuum closure plate | Move MPR to the vacuum closure plate | Movement | 0.00066934 | 145.1304 |  |  | N/A | Multi-purpose robot (transport) | RM tool storage | Lower Port | 2 | 0.83 | 0.00066934 |  | N/A |  | N/A | N/A
| Remove sealing face protection | Operation | 3.4788 | 148.6092 | Remove vacuum sealing face guards | MPR | 3.4788 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Move MPR away from the port door | Movement | 0.0043507 | 148.6135 |  |  | N/A | Multi-purpose robot (transport) | Lower port | Hot Cell Interface | 13 | 0.83 | 0.0043507 |  | N/A |  | N/A | N/A
| Close VCP | Operation | 2.3036 | 150.9171 | Close VCP | VCP handling frame; bolt runners | 2.3036 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Release VCP handling fixations | Operation | 0.0243 | 150.9414 | Actuate handling interfaces | VCP handling frame | 0.0243 |  |  |  | N/A | N/A | N/A | actuate handling fixations | N/A |  | N/A | N/A
| Move VCP handling frame away from the VCP | Operation | 2 | 152.9414 | Move VCP handling system away from the VCP | VCP handling frame | 2 | Multi-purpose robot (transport) | Hot Cell Interface | Lower Port | 13 | 0.83 | N/A |  | N/A |  | N/A | N/A
| Seal the VCP | Operation | 1.8554 | 154.7968 | Seal VCP using autonomous bolt runners | VCP handling frame; bolt runners | 1.8554 |  |  |  | N/A | N/A | N/A |  | N/A | Store inner threshold rails; collect new VCP fixations from RM stores; transport into lower port hot cell; move to laydown area using the overhead crane | 146.4908 | 6.4506
| Confirm VCP is sucessfully sealed | Operation | 3.7722 | 158.569 | Perform engineering checks | MPR | 3.7722 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Perfrom health physics checks to confirm seal is suitable | Operation | 3.7722 | 162.3413 | Perform Health Physics Checks | MPR | 3.7722 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Store autonomous bolt runners in the nearby tool storage | Logistics | 0.0492 | 162.3905 |  |  | N/A |  |  |  | N/A | N/A | N/A | Store / collect RM equipment from laydown area | 0.0492 |  | N/A | N/A
Remove VCP handling frame and all RM tooling from the hot cell | Move overhead crane to the lower port | Movement | 0.018056 | 162.4085 |  |  | N/A | Overhead crane (unloaded) | Hot Cell Interface | Lower Port | 13 | 0.2 | 0.018056 |  | N/A |  | N/A | N/A
| Collect VCP tool storage | Logistics | 0.336 | 162.7445 |  |  | N/A |  |  |  | N/A | N/A | N/A | Store / collect items with the overhead crane | 0.336 |  | N/A | N/A
| Move tool storage to the hot cell interface | Movement | 0.18056 | 162.9251 |  |  | N/A | Overhead crane (loaded) | Lower port | Hot Cell Interface | 13 | 0.02 | 0.18056 |  | N/A |  | N/A | N/A
| Place tool storage onto the hot cell interface | Logistics | 0.336 | 163.2611 |  |  | N/A |  |  |  | N/A | N/A | N/A | Store / collect items with the overhead crane | 0.336 |  | N/A | N/A
| Move overhead crane to the lower port | Movement | 0.018056 | 163.2791 |  |  | N/A | Overhead crane (unloaded) | Hot Cell Interface | Lower Port | 13 | 0.2 | 0.018056 |  | N/A |  | N/A | N/A
| Engage the handling interface with the VCP handling frame | Logistics | 0.336 | 163.6151 |  |  | N/A |  |  |  | N/A | N/A | N/A | Store / collect items with the overhead crane | 0.336 |  | N/A | N/A
| Actuate the lifting frame fixation interfaces | Operation | 0.0243 | 163.6394 | Actuate handling interfaces | VCP handling frame; overhead crane | 0.0243 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Move the lifting frame to the lower port | Movement | 0.18056 | 163.82 |  |  | N/A | Overhead crane (loaded) | Lower port | Hot Cell Interface | 13 | 0.02 | 0.18056 |  | N/A |  | N/A | N/A
| Place lifting frame onto the hot cell interface | Logistics | 0.336 | 164.156 |  |  | N/A |  |  |  | N/A | N/A | N/A | Store / collect items with the overhead crane | 0.336 |  | N/A | N/A
Recommission the bioshield door movers and close bioshield doors | Move MPR to the bioshield doors | Movement | 0.0033467 | 164.1593 |  |  | N/A | Multi-purpose robot (transport) | Lower port | PP hardware stillage | 10 | 0.83 | 0.0033467 |  | N/A |  | N/A | N/A
| Recommission the first bioshield door mover | Logistics | 0.6233 | 164.7826 |  |  | N/A |  |  |  | N/A | N/A | N/A | Make and commission RM service connections | 0.6233 |  | N/A | N/A
| Seal bioshield door | Operation | 1.336 | 166.1186 | Move Lower Port bioshield door | Bioshield door movers; | 1.336 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Move MPR to the sealed bioshield door | Movement | 0.0033467 | 166.122 |  |  | N/A | Multi-purpose robot (transport) | PP hardware stillage | Lower Port | 10 | 0.83 | 0.0033467 |  | N/A |  | N/A | N/A
| Carry out engineering checks to confirm door sealed sucessfully | Operation | 3.7722 | 169.8942 | Perform engineering checks | MPR | 3.7722 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Carry out health physics tests to confirm door sucessful closure of lower port | Operation | 3.7722 | 173.6664 | Perform Health Physics Checks | MPR | 3.7722 |  |  |  | N/A | N/A | N/A |  | N/A |  | N/A | N/A
| Disconnect first bioshield mover | Logistics | 0.188 | 173.8544 |  |  | N/A |  |  |  | N/A | N/A | N/A | Disconnect RM services | 0.188 |  | N/A | N/A
| Collect bioshield mover with the MPR | Logistics | 0.0492 | 173.9036 |  |  | N/A |  |  |  | N/A | N/A | N/A | Store / collect RM equipment from laydown area | 0.0492 |  | N/A | N/A
| Move bioshield mover to the hot cell interface | Movement | 0.0043507 | 173.908 |  |  | N/A | Multi-purpose robot (transport) | Lower port | Hot Cell Interface | 13 | 0.83 | 0.0043507 |  | N/A |  | N/A | N/A
| Deposit first bioshield mover | Logistics | 0.0492 | 173.9572 |  |  | N/A |  |  |  | N/A | N/A | N/A | Store / collect RM equipment from laydown area | 0.0492 |  | N/A | N/A
| Move back to the lower port | Movement | 0.0043507 | 173.9615 |  |  | N/A | Multi-purpose robot (transport) | Hot Cell Interface | Lower Port | 13 | 0.83 | 0.0043507 |  | N/A |  | N/A | N/A
| Disconnect second bioshield mover | Logistics | 0.188 | 174.1495 |  |  | N/A |  |  |  | N/A | N/A | N/A | Disconnect RM services | 0.188 |  | N/A | N/A
| Collect second mover with the MPR | Logistics | 0.0492 | 174.1987 |  |  | N/A |  |  |  | N/A | N/A | N/A | Store / collect RM equipment from laydown area | 0.0492 |  | N/A | N/A
| Transport back to the hot cell interface | Movement | 0.0043507 | 174.2031 |  |  | N/A | Multi-purpose robot (transport) | Lower port | Hot Cell Interface | 13 | 0.83 | 0.0043507 |  | N/A | Remove and store VCP tooling; return ex-vessel hardware to collect more RM equipment from the hot cell | 144.3507 | 29.848
Remove all RM equipment from the lower port hot cell | Move overhead crane to the final RM tool storage location | Movement | 0.0083333 | 174.2114 |  |  | N/A | Overhead crane (unloaded) | Hot Cell Interface | RM equipment stillage | 6 | 0.2 | 0.0083333 |  | N/A |  | N/A | N/A
| Collect RM tool storage | Logistics | 0.336 | 174.5474 |  |  | N/A |  |  |  | N/A | N/A | N/A | Store / collect items with the overhead crane | 0.336 |  | N/A | N/A
| Move overhead crane to hot cell interface | Movement | 0.083333 | 174.6307 |  |  | N/A | Overhead crane (loaded) | RM equipment stillage | Hot Cell Interface | 6 | 0.02 | 0.083333 |  | N/A |  | N/A | N/A
| Deposit tool storage onto the interface | Logistics | 0.336 | 174.9667 |  |  | N/A |  |  |  | N/A | N/A | N/A | Store / collect items with the overhead crane | 0.336 |  | N/A | N/A
| Move overhead crane to the MPR | Movement | 0.083333 | 175.0501 |  |  | N/A | Overhead crane (loaded) | Hot Cell Interface | RM equipment stillage | 6 | 0.02 | 0.083333 |  | N/A |  | N/A | N/A
| Collect MPR with the overhead crane | Logistics | 0.336 | 175.3861 |  |  | N/A |  |  |  | N/A | N/A | N/A | Store / collect items with the overhead crane | 0.336 |  | N/A | N/A
| Move to hot cell interfaces | Movement | 0.083333 | 175.4694 |  |  | N/A | Overhead crane (loaded) | RM equipment stillage | Hot Cell Interface | 6 | 0.02 | 0.083333 |  | N/A |  | N/A | N/A
| Place MPR onto the interface | Logistics | 0.336 | 175.8054 |  |  | N/A |  |  |  | N/A | N/A | N/A | Store / collect items with the overhead crane | 0.336 |  | N/A | N/A
| Transfer final items of RM tooling out of the hot cell | Logistics | 0.214 | 176.0194 |  |  | N/A |  |  |  | N/A | N/A | N/A | Transfer equipment to/from port interface | 0.214 |  | N/A | N/A
Divertor Installation Complete | End Time |  |  | 124.8029
| Operational Time |  |  | 93.5525 | 74.96%
| Logistical Time |  |  | 21.6288 | 17.33%
| Movement Time |  |  | 5.4664 | 4.38%
| Logisitcal Delay |  |  | 4.1552 | 3.329%
Hardware Installation Complete | End Time |  |  | 176.0194
| Operational Time |  |  | 135.3752 | 76.91%
| Logistical Time |  |  | 28.9804 | 16.46%
| Movement Time |  |  | 7.0052 | 3.98%
| Logisitcal Delay |  |  | 4.6586 | 2.647%
Divertor Maintenance Cycle Complete | End Time |  |  | 253.9345
| Operational Time |  |  | 198.1303 | 78.02%
| Logistical Time |  |  | 39.2829 | 15.47%
| Movement Time |  |  | 10.5433 | 4.152%
| Logisitcal Delay |  |  | 5.978 | 2.354%
Full Maintenance Cycle Complete | End Time |  |  | 335.1538
| Operational Time |  |  | 263.7766 | 78.7%
| Logistical Time |  |  | 51.6963 | 15.42%
| Movement Time |  |  | 13.1994 | 3.938%
| Logisitcal Delay |  |  | 6.4814 | 1.934%